## Task List
NWS Flood Inundation Mapping - Project Development Template | [7 empty] | Version 0.12
PROJECT INFORMATION |  |  |  | Stage (ft) | Elevation (ft) NAVD88 |  |  | List of Stages:
Project Name: | Fort Wayne |  | Highest inundation Stage: | 22 | 770.46 |  |  | 12, 13, 14, 15,16, 17, 18, 19, 20, 21, 22
River: | St. Mary's River |  | Major Flood Stage: | 19 | 767.46
NWS Site Description: | St. Mary's River at Muldon Br. |  | Moderate Flood Stage: | 17 | 765.46
USGS Site Description: | ST. MARYS RIVER NEAR FORT WAYNE, IN |  | Flood Stage: | 14 | 762.46 |  |  | PROJECT TEAM WORK RESPONSIBILITY MATRIX KEY
Gage County, State: | Allen County, Indiana, Hydrologic Unit 04100004 |  | Action Stage: | 12 | 760.46 |  |  | R = Responsible |  |  | This individual(s) is (are) responsible for
AHPS Gage NWSLID: | SASI3 |  | Lowest inundation Stage: | 12 | 760.46 |  |  |  | the activity and associated action items.
USGS Gage ID: | 04182000 |  | Gage 0 Datum: | 0 | 748.46 |  |  | A = Accountable |  |  | This individual(s) is (are) accountable for
NWS WFO: | IND |  | Mapping Interval (ft): | 1 |  |  |  |  | the activity based on the individual(‘s) job description.
NWS RFC: | OHRFC |  | NGVD29 to NAVD88 Offset Value (ft): | -0.512 |  |  |  | C = Consult |  |  | This (these) individual(s) should be consulted,
U\S Reach Length (mi): | 0 (Gage) | [7 empty] | as part of the communication, coordination, cooperation,
D\S Reach Length (mi): | 8.5 (D\S of Main St) | [7 empty] | and collaboration required for effective management
Map Display Scale: | 1:6,000 |  | Gage Latitude (DD): | 40°59'16" |  | NAD83 |  |  | of flood hazards.
FEMA FIS Date & Type: | DFIRM & FIS August 2009 |  | Gage Longitude (DD): | 85°06'43" |  | NAD83 |  | I = Inform |  |  | Knowledge should be readily available to
| 0.2%: 770.2 ft ;1%-769 ft ; 2%- 768 ft ;10% - 765.5 ft NAVD88 | [7 empty] | this (these) individual(s).
PROJECT TEAM - CONTACTS, ROLES AND RESPONSIBILTIES | [5 empty] | Coordinator | HPM | QC Team | RFC Hydrologist | FIM Prog Mngr | AHPS Web Team | Coordinator | Hydraulic Modeler | GIS Analyst | Water Science Ctr | Local Stakeholder
[8 empty] | NWS |  |  | NWS |  | Technical |  | USGS | Local
Organization | Project Role | Name | E-mail | Phone | Responsibilities | [5 empty] | AHPS |  | Partner
NWS | Coordinator | Kris Lander | kris.lander@noaa.gov | 816-268-3124 | Overall coordination of the project. Responsible for project management, guiding partners and completing AHPS implementation. | X
| HPM | Mike Rehbein | Michael.Rehbein@noaa.gov | 574-834-1104 x 493 | NWS forecast services and serves as primary contact with local stakeholders. |  | X
| QC Team | Darrin Hansing | Darrin.Hansing@noaa.gov |  | Conducts QAQC review of Hydraulic Analyses and GIS data in Phase 2A & 2B. |  |  | X
| RFC Hydrologist | Jim Noel | james.noel@noaa.gov | 937-383-0527 | Support for rating curve evaluation and develops RFC forecast services. |  |  |  | X
| FIM Prog Manager | Victor Hom | victor.hom@noaa.gov |  | Approves and advises on non-standard project approaches. |  |  |  |  | X
NWS AHPS Web Team | AHPS Web Team | John Bolinger | John.Bollinger@noaa.gov |  | Implements GIS deliverables into AHPS Web Team interface in Phase 3. | [5 empty] | X
Technical Partner | Partner Coordinator | Moon Kim | mkim@usgs.gov | 317-600-2787 | Overall coordination of the technical team. Responsible for Phase 2A & 2B deliverables. | [6 empty] | X
| Hydraulic Modeler |  |  |  | Develops and calibrates hydraulic model and associated documentation. | [7 empty] | X
| GIS Analyst |  |  |  | Develops GIS data deliverables in Phase 2A. Provides GIS support to the project. | [8 empty] | X
USGS | Water Science Center | Moon Kim | mkim@usgs.gov | 317-600-2787 | Provides hydrologic data support as required. | [9 empty] | X
Local | Local Stakeholder | Cathy Robb, City of Fort Wayne, IN | Cathy.Robb@ci.ft-wayne.in.us | 260-427-2821 | Central point of contact for local interests. Provides input on product decisions. Coordinates and collects input from other local stakeholders. | [10 empty] | X
PHASE 1 - PROJECT SCOPING AND PLANNING | [5 empty] | Coordinator | HPM | QC Team | RFC Hydrologist | FIM Prog Mngr | AHPS Web Team | Coordinator | Hydraulic Modeler | GIS Analyst | Water Science Ctr | Local Stakeholder
Status | Task | Explanation | Actions | Guidance | Comments |  |  | NWS |  |  | NWS |  | Technical |  | USGS | Local
[11 empty] | AHPS |  | Partner
NWS Internal Pre-Scoping and Pre-Proposal Writing Activities
Completed | Site-Suitability Evaluation | NWS will evaluate the suitability of the proposed site for AHPS static flood inundation mapping. Areas of program consideration include: value to the NWS AHPS program, and the value to local communities and evaluation of project funding sources. Areas of technical consideration include: stability of the operational rating curve (locations with ratings that shift frequently or significantly cannot be considered), hydrologic complexity, hydraulic complexity, flood history, time since most recent flood or other factors that may warrant static flood inundation mapping inappropriate for implementation. | NWS Coordinator and HPM will evaluate the value to the NWS AHPS program, the value to local communities and evaluation of project funding sources. NWS Coordinator will document the flood crest history on the [Flood Impacts] page. The RFC hydrologist will evaluate the rating curve and determine stable the rating curve is stable. NWS Coordinator, HPM and RFC will evaluate the hydrologic complexity, hydraulic complexity and other factors that may warrant flood inundation mapping in appropriate for implementation. The NWS Coordinator will make a Go or No Go decision on the project. | N/A | This approval is for SASI3, which is a current forecast point. FWAI3 was not selected due to fact that FWAI3 cannot be made into a forecast point for several years due to the short record (< 1 yr) and no rating. | R | A |  | C | C |  | I
Completed | AHPS Level Of Service Review | NWS will verify the USGS gage location is an existing AHPS forecast point or data point. If an AHPS forecast point or data point does not exist, determine if an AHPS forecast point can be created. Verify the appropriate level of forecast service (flood only or daily; WFO SSHP or RFC) exists at the AHPS forecast point. Determine if an existing data point should be upgraded to a forecast point. Apply for NWSLID for new forecast points. | NWS Coordinator will work with the HPM and RFC to complete AHPS Level Of Service review and associated actions. | 2.1 |  | R | A |  | C |  |  | I
Completed | AHPS Gage Location Check | NWS will verify the USGS gage location is correctly displayed on the AHPS page. | The NWS Coordinator will cross-check the current AHPS gage location with the known USGS gage location. The NWS HPM will make corrections to the AHPS page, if corrections are necessary. The NWS Coordinator will clip a photo from the USGS Site Information page on NWIS and paste it in the [Location Map] tab. | N/A | AHPS shows forecast point located in WFO IND's area. | R | A |  | I |  |  | I |  |  | C
Completed | Review/Create/Update AHPS Flood Impact Statements | NWS will verify that the AHPS flood impact statements are current for existing forecast points. NWS will create flood impact statements for new forecast points. | NWS Coordinator and HPM will verify that the AHPS flood impact statements are current for existing forecast points. NWS HPM will create flood impact statements for new forecast points. NWS Coordinator or HPM may consult with local stakeholders on flood impacts. NWS will populate AHPS flood impacts in the [Flood Impacts] tab. | N/A |  | R | A |  | C |  |  | I |  |  |  | C
Completed | Review/Create/Update AHPS Flood Categories | NWS will verify that the AHPS flood categories are current for existing forecast points. NWS will create flood categories for new forecast points. | NWS Coordinator and HPM will verify that the AHPS flood categories are current for existing forecast points. NWS HPM will create flood categories for new forecast points. NWS HPM may consult with local stakeholders on flood categories. | N/A |  | R | A |  | C |  |  | I |  |  |  | C
Completed | Project Development Template Setup | The Project Development Template will be used as a project management tool and a guide to developing a FIM project. The Project Development Template is used to assign roles and responsibilities, track task progress, document decisions, document project data and schedule. | NWS Coordinator will setup the Project Development Template. NWS Coordinator is responsible for continuously updating and distributing the checksheet to the team during the project lifecycle. The NWS Coordinator will determine which OPTIONAL tasks are required. Other members of the project team may contribute to the Project Development Template throughout the project. | N/A |  | R
Pre-Scoping and Project Planning Activities
Completed | AHPS Implementation Process Overview | NWS will explain the sequence of tasks required to implement a library on AHPS and explain the guidelines that maps should be developed to. | NWS Coordinator will provide Technical Partner with a copy of the Project Development Template. NWS will explain the process, explain the roles of the project team members and answer Partner questions. NWS will demonstrate an existing AHPS FIM to partner. | 1.5 |  | R | [5 empty] | I | I | I
Completed | NWS Flood Inundation Mapping Tools for GIS | A set of QC tools are available from the NWS to review GIS data. NWS will provide a copy of the tools to Technical Partner and provide instructions on how to install and operate tools. | NWS Coordinator will provide Technical Partner with a copy of "NWS Flood Inundation Mapping Tools" for ESRI ArcGIS 10.0. | N/A |  | R | [5 empty] | I | I | I
Not Applicable | Timeline | Establish a baseline project timeline in the Project Development Template. NWS will need to review the queue of previously scheduled FIM projects and ensure that the proposed project schedule can be accommodated with the NWS production schedule. | NWS Coordinator and Technical Partner will work together to complete a baseline estimate of the project tasks in the Gantt chart in the [Timeline] tab. NWS will validate that the proposed project schedule can be accommodated. | 2.1 |  | R | [5 empty] | A
Completed | Project Team Work Responsibility Matrix | Determine the project team work responsibilities and document the responsibilities in the Project Development Template. | NWS Coordinator and Technical Partner will coordinate the completion of the "Project Team Work Responsibility Matrix" in the Project Development Template. | N/A |  | R | [5 empty] | A
Completed | Identify Project Cost & Funding Sources | Identify the AHPS project cost, the map development project costs (if applicable) and source of funding for AHPS implementation and for map development tasks (if applicable). | NWS Coordinator will contact AHPS Web Team to obtain a quote for AHPS implementation costs. Local Stakeholders who have not identified a Technical Partner should make a selection and identify costs for map production. NWS and Local Stakeholders should identify a funding source for AHPS implementation. | N/A |  | R |  |  |  |  | C | I | I | I |  | C
In Progress | Statement of Work - AHPS Implementation | Create a SOW document if the project is to be funded outside of an existing contract. Funding must be identified and a contract must be in process with AHPS Web Team before Phase 2A begins. If funded through the existing contract, start the transfer of funds. | NWS Coordinator, Local Stakeholder and AHPS Web Team to complete Statement of Work Document for the AHPS Implementation. Existing contract projects should start the transfer of funds for AHPS implementation. | 2.5 | HIF Contract. Orion has not been paid. | R |  |  |  |  | A |  |  |  |  | A
Not Applicable | Statement of Work - Map Development Tasks (OPTIONAL) | NWS will work with the local stakeholder and its mapping partners\subcontractors (as necessary), to develop a Statement Of Work (SOW) that will guide the production of inundation mapping at a river forecast point. This may only be required when a local or state government partner hires an engineering consultant or contracts with another government entity to serve as the Technical Partner. | NWS, Local Stakeholders and the contracted Technical Partner should complete the Statement of Work Document for the development of the inundation maps. | 2.5 & Appendix A |  | R | [5 empty] | A | C | C |  | A
Completed | Local Stakeholder Preferences for Modeling | Consult with local stakeholders on their preferences for modeling, including any Local Emergency Action Plans that detail the deployment of temporary flood protection measures in the hydraulic model and mapping. Input on the inclusion of unaccredited levees in the model should be discussed. Preferences for the display of risk areas behind levees in the AHPS site should be discussed. Preferences for the elevation to model at a location (i.e. if levees should be shown as overtopped) should be discussed. | NWS Coordinator and NWS HPM will contact Local Stakeholder and inquire about including the following features in the model (1) EAPs, (2) temporary flood protection measures, (3) unaccredited levees. NWS Coordinator and NWS HPM will identify the local preferences for elevation and risk area display. | N/A | USGS was coordinating directly with Cathy Robb from the City of Fort Wayne, IN. Local stakeholder decided not to overtop levees in AHPS scenario. | R | A |  |  |  |  | I | I | I |  | C
Completed | Identify Known Flood Impacts and Impact Related GIS Data | NWS and Technical Partner will assemble all known data on the location, elevation/stage and severity of flood impacts. Information sources may include FEMA FIS, FEMA DFIRM GIS data, review of known federal levees in the USACE National Levee Database, review of areal photography of the site, NWS e-19 data or historical accounts. Collect and review existing GIS data sources to assist with the scoping of the project. General feature Layers to collect include: model cross-sections, NHD stream centerlines, city boundaries, HUC boundaries, stream gage locations, DFIRM data, flood control structures, critical infrastructure. All flood impact data will be adjusted to a common NAVD88 vertical datum. | Technical Partner will plot all relevant GIS impact data on the [Location Map] "Impacts Map" by exporting the map into a jpeg or gif graphical format. Technical Partner will list the stage and elevation of known flood impacts in the [Flood Impacts] tab, in addition to previously entered NWS impact data. The Technical Partner will adjust the flood impact data to a common NAVD88 vertical datum. | N/A |  | C | C |  | C |  |  | R | A | A |  | C
Completed | Obtain FEMA FIS and DFIRMs (OPTIONAL) | Determine if a FEMA FIS was completed at this project location (edd.msc.fema.gov). Obtain a copy of the FIS and a copy of the DFIRM, if available. Determine if the DFIRM is recent enough to be considered valid. If the DFIRM is considered current, then the equivalent stages produced by the hydraulic modeling should agree with the DFIRM. | Technical Partner will obtain a copy of the FIS and/or DFIRM GIS files. NWS may assist in contacting local stakeholders for information. | N/A |  | C | C |  |  |  |  | R | A | A |  | C
Completed | Hydraulic Modeling Approach & Model selection | Establish suitability of 1-D or 2-D modeling approach and static map library. Review the need to develop a steady or unsteady model. Evaluate the presence of levees, floodwalls or significant floodplain storage areas. Select FEMA approved hydraulic model. | NWS Coordinator and Technical Partner will review known flood impacts and GIS data and determine if the site is suitable for static mapping. Technical Partner will propose a FEMA approved 1-D or 2-D modeling approach to be run in steady or unsteady model. The NWS & Technical Partner should have a concensus agreement on the approach, before moving forward with the project. | 3.2.1 | HEC-RAS is FEMA approved. Model approach approved. Previous studies have been done on this reach with HEC-2. | A | C | C | C | I |  | R | A
Completed | Terrain Data Identification | Identify the best available terrain data and verify that the terrain data set meets NWS guidelines and has a vertical accuracy greater or equal to a 2-ft contour interval. Lidar data are preferred whenever possible. A DEM format is preferred. DEM Grid cell sizes of 3 m or less are preferred. DEM Grid cell sizes of 10 m or less are required. A Draft Terrain Footprint shapefile will be developed to help the NWS and Technical Partner to visualize any constraints that may exist. | Technical Partner will research and identify the best available terrain data set. Technical Partner will obtain the metadata for the selected terrain data set and submit the metadata to NWS Coordinator for documentation of data quality. The Technical Partner will develop a Draft Terrain Footprint (see Deliverable Checklist) and deliver the shapeifle to the NWS Coordinator. Note: the entire terrrain data set will not be submitted in this step, only the metadata and footprint. NWS Coordinator will review metadata and approve proposed terrain data set. | 3.1.6.3 |  | C | [5 empty] | R |  | A
Site Selection and Evaluation Scoping
Completed | Reach Length | Establish the upstream and downstream boundaries of the project. The project extent should incorparate most or ALL of the AHPS flood impacts published on the AHPS web page. Evaluate study extent impact on AHPS web appearance. Ensure that terrain data and a hydraulic model are available or can be created within the boundaries of the desired extent. Review site for possible backwater effects from downstream confluences and/or structures. Evaluate the impact of local flows to cause the WSE on the upstream and downstream boundaries to vary by more than 2 mapping intervals from the WSE at the gage. If the reach length extends beyond a "Standard Project Length" of 5 miles upstream or 5 miles downstream from the gage, complete a Reach Length Hydrologic Analysis in the [Local Flow Analysis] tab. | Technical Partner will create an "Overview Map" and plot the study extend boundaries on [Location Map] by exporting the map in a jpeg or gif format. NWS Coordinator will enter U\S and D\S reach length on the Project Development Template. NWS HPM will coordinate reach length with the Local Stakeholder. The NWS Coordinator and RFC will conduct a Reach Length Hydrologic Analysis in the [Local Flow Analysis] tab for projects that extend beyond a "Standard Project Length" of 5 miles upstream or downstream from a gage. | 2.4.1 & 3.2.1.3 | Entire reach will be mapped between Muldoon (upstream from Ferguson Rd. East) and Main St. Bridge, with the understanding that the hydraulic model verification must support the 9 mile lenght of reach. At a future date, the reach may be split into two, approximately 4.5 mile segments and the downstream reach would be tied to the FWAI3 gage. Input was recieved from Cathy Robb of the City of Ft. Wayne on flood impacts along the reach. | R | C |  | C |  |  | A | C | A |  | C
Completed | Mapping Intervals | The minimum requirement is that layers must be created at 1.0 ft intervals for ALL elevations from Flood Stage to the Highest Elevation modeled. From Action Stage up to Flood Stage a maximum spacing of 2.0 ft can be applied; however, the spacing must (1) consider flood impacts and must hit the flood impacts, and (2) must provide potential future flexibility for lowering or adjusting flood stage an Action Stage. Mapping intervals should not be smaller than 1/2 the equivalent contour interval. | NWS Coordinator will conduct a scoping meeting to discuss and select mapping intervals. The NWS Service Hydrologist must verify that the selected mapping intervals aligns with the AHPS flood categories or any known future plans to adjust the AHPS flood categories. NWS Coordinator will create a "List of Stages" to be modeled at the header of the Project Template. The Technical Partners wil review and approve the NWS proposed stages. | 2.4.2 |  | R | C |  | C |  |  | C | C | C |  | C
Completed | "Gage 0" Vertical Datum | Determine the quality of the vertical datum used to define the "Gage 0" at the USGS stream gage. Determine if gage was surveyed or estimated. If the datum was not established from a survey-grade source, then the "Gage 0" value must be surveyed. Establish conversion from gage datum to NAVD88 if necessary. Use VERTCON as the basis for datum conversions from NGVD29 to NAVD88. A link to VERTCON and VERTCON worksheet are available in the [Spatial Calc] tab. | NWS Coordinator will contact USGS Water Science Center and inquire about the methods used to determine the "Gage 0" datum. USGS Water Science Center will report to the NWS the methods used to determine the "Gage 0" datum to the NWS. NWS will document VERTCON calculations in the [Spatial Calc] tab. NWS will document "Gage 0" quality in Comments ==> and in the [Spatial Calc] tab. | 3.1.8 |  | R | A |  |  |  |  | I | I | I | C
Completed | Measured Rating Curve Quality Check | Obtain the USGS rating curve from the USGS Rating Depot. Verify historical changes to datum and/or location of gage at forecast point location. Verify that the current USGS rating is well defined by streamflow measurements. If a well defined rating curve is not available, then determine if a rating curve can be developed by USGS prior to hydraulic model development or if a synthetic rating curve should be developed from the model. | NWS Coordinator will obtain the USGS measured rating curve from the USGS Rating Depot and discuss rating quality with the USGS WSC. NWS Coordinator will also consult with RFC on rating quality. NWS will copy the USGS rating into the [Rating] tab on the Project Development Template. The Technical Partners will review and discuss the rating curves with the NWS. | 2.1 | Gage has been present since Nov. 7, 1930 so rating has been well-established over years. The downstream gage at Ft. Wayne is fairly new started Oct. 2009. | R | A |  | C |  |  | C | C | C | C
Completed | USGS and NWS Rating Curve Comparison | Obtain the rating curve from the NWS River Forecast Center. Copy both ratings into the [Rating] tab on the Project Development Template. Plot and compare the NWS RFC rating and the USGS gage rating. Ensure that the ratings agree. If ratings do not agree, coordinate the development of a common rating curve, before hydraulic modeling begins. | NWS Coordinator will obtain the RFC operational rating curve from the NWS RFC. NWS Coordinator will copy the USGS rating into the [Rating] tab on the Project Development Template. The Technical Partners will review and discuss the rating curves with the NWS. | N/A | OHRFC has provided a copy of the rating curve. OHRFC has verified the rating is the current USGS rating. | R |  |  | A |  |  | C | C | C | C
Completed | Rating Curve Extension Check | NWS will verify that the USGS rating curve covers the full range of flood impact stages. The NWS may also use the model as a means to extend the rating curve to support RFC forecast operations at or above the maximum FIM elevations. If it is determined that the rating curve, requires an extension, then the USGS should be consulted on the feasibility of an extension. If the USGS cannot provide an extension, then the model will be used as the basis for extension. | NWS Coordinator, RFC and Technical Partners will review the rating curve and coordinate any rating extensions. The RFC will provide RFC operational requirements for a rating extension. The Technical Partners will consult with and coordinate any rating extensions with the USGS. | N/A |  | R |  |  | C |  |  | C | C | C | C
Completed | Establish Minimum/Maximum Stage | The lowest modeled inundation WSELs should be representative of bankful conditions and should be set at a minimum to Action stage. The lowest modeled inundation WSEL may be revised in Phase 2A of the study, if it is found that the lowest WSEL does not adequately represent bankful conditions. The highest modeled inundation elevations (WSELs) may exceed the rating, if either a USGS rating extension is available or if the model is capable of simulating the WSEL at the highest stage. | NWS Coordinator and NWS HPM will coordinate with Technical Partner and Local Stakeholder to establish the minimum and maximum stage. Local Stakeholders will comment on if the min and max stages meet local needs. | N/A | Max stage established at 22-ft, instead of 23-ft, because a Left levee overtops at 23-ft. | R | A |  | C |  |  | A | C | C |  | C
Hydraulic Model Scoping
Completed | Hydraulic Structures Inventory | Create an inventory of hydraulic structures that fall within the Study Area boundary on the [Structures] tab. Bridges, levees (federal & non-federal), floodwalls, low head dams, lock & dams, and temporary measures should be considered. Determine the critical elevations of levees and bridges that may impact modeling decisions. | Technical Partner will create an inventory of hydraulic structures that fall within the Study Area boundary on the [Structures] tab. NWS and Technical Partner will coordinate on which structure geometry will need to be included in the model by flagging the [Structures] field "Included in Hydraulic Model?" with Yes or No. | 3.1.4 |  | C | C |  |  |  |  | R | A | A
Completed | Obtain & Review Hydraulic Model Geometry | Determine if a new model will be created or if an existing model can be updated. Research any existing hydraulic models. Initial preference is for an existing FEMA FIS. Check the model vertical datum for NAVD88 compliance. Determine if legacy FEMA FIS models are georeferenced. | Technical Partner will check with state NFIP coordinator to identify any existing FEMA FIS studies, studies that are in progress or studies that are preliminary. Technical Partner will obtain FEMA datasets if appropriate and available. Technical Partner will propose an approach to developing model geometry. NWS will review and approve the approach. | 3.2.1.2 | An existing model done in HEC2 10/92 was aquired. Some of the bridge data was used when verifying same structure exists today. | C | [5 empty] | R | A | A
Completed | Hydraulic Structure Verification | Coordinate with local public works or state transportation agency to verify hydraulic model represents current bridge/structure and to determine imminent plans for structure replacement and/or revision. Determine if an major construction projects are planned that modify existing structure or add new structures and may impact the quality of the maps. Determine the authoritative data sources for hydraulic structure elevations, including flood control structures. As-built plans, Lidar or surveying are possible sources. | NWS and Technical Partner will consult with the local stakeholder to determine if changes to channel or structures may be planned. NWS and Technical Partner will coordinate a review of the data entered in the [Structures] tab with the local stakeholders to determine if the inventory is accurate and complete and that the best available data are used for structure elevation. | N/A |  | R | A |  |  |  |  | A | A | A |  | C
Completed | Surveying Requirements | Determine if surveying work will be required to obtain structural elevation information. | Technical Partner will determine if existing structural geometry data meets the needs of the project. Technical Partner will collect additional survey information as needed. | N/A |  | C | [5 empty] | R | A | A
Completed | Hydraulic Modeling Calibration and Validation Data Collection | Identify sources of data that may be used to calibrate and validate the hydraulic model. A rating curve will be used for calibration at the gage. Sources of High Water Mark (HWM) data, aerial photography taken during a flood, Lidar data flow during a flood, historical flood study reports should be identified. The model must be calibrated to agree with the measured rating curve, at each stage\elevation target, to within 0.5 ft or 1/2 a mapping interval (whichever is less) for all stages above flood stage. | Technical Partner will consult with the Local Stakeholders, USGS, or other state\federal partners to identify data sources for model calibration/validation. The Technical Partner will collect data sources. The Technical Partner will calibrate the model to agree with measured rating curve, at each stage\elevation target, to within 0.5 ft or 1/2 a mapping interval (whichever is less) for all stages above flood stage. | 3.2.1.2 |  | C | C |  |  |  |  | R | A |  | C | C
Completed | Flood Control Structure Modeling Approach | Finalize the approach to modeling flood control structures or temporary measures that will be overtopped. Discuss and decide how the impacts of overtopping and risk areas behind flood control structures will be shown on AHPS. | Technical Partner will develop a modeling strategy for representing flood control structures, using a method that meets the needs of the local stakeholders. | 3.3.1 | Flood control structures will not overtop | C | [5 empty] | R | C | C |  | C
GIS Product Scoping
Completed | Obtain & Review Terrain Data | Obtain a copy of the best available terrain data set, the terrain metadata and verify that the terrain data set has a vertical accuracy greater or equal to a 2-ft contour interval. Lidar data should be processed into a terrain surface. Determine if the DEM derived from the lidar data has a horizontal grid cell size of 10-m or smaller. A 3-m or smaller DEM is preferred, and the 3-m or smaller grid will require significantly less effort to develop and revise flood inundation maps. Check the model vertical datum for NAVD88 compliance. Populate the terrain metadata fields in the [Terrain] tab. | Technical Partner will obtain the terrain data and provide NWS with terrain metadata showing that it meets NWS Guidelines. Technical Partner will provide the NWS with a shapefile that represents the footprint of the terrain data. Technical Partner will populate the terrain metadata in the [Terrain] tab. | 3.1.6.3 | 3-m lidar. Lidar data is adequate quality and will support 1 ft depth increments. | C | [5 empty] | R | A | A |  | C
Completed | Grid and Polygon Map Development Technique | Determine how GIS data will be processed from the hydraulic model. NWS and mapping partner will discuss the advantages of processing data with a 3-m or smaller grid cell size. With a 3-m or small grid cell size, the, polygons may be produced directly from the raster data. The depth grid cell size must be supported by an underlying terrain data cell size that is equal to or smaller than the depth grid cell size. | NWS and Technical Partner will discuss the options and decide on a depth grid cell size. The depth grid cell size will be documented in "Comments" ==> | 3.1.6.3 |  | C | [5 empty] | R | A | A
Completed | Preliminary Map Display Scale | Calculate the intended map display scale based upon the underlying terrain data set DEM cell size. The map display scale will be calculated by multiplying the DEM grid cell diameter (in meters) by 2,000 pixels/meter to get the standard display scale in a standard 1 inch = X feet or 1:X ratio. | Technical Partner will calculate the Map display scale and enter in the Project Development Template header. | 3.6 |  | C | [5 empty] | R | A | A
Local Stakeholder Review
Completed | Local Stakeholder Review Meeting | Present the project to the stakeholders. Obtain stakeholder input on the known flood impacts, NWS flood categories, lowest/highest inundation elevation, mapping interval and study area extent. Stakeholders should also provide information on Emergency Action Plans where temporary protection measures may be deployed. Stakeholders should provide input on if they want the EAP temporary measures considered in the hydraulic modeling. | NWS HPM will coordinate the scoping project decisions with the Local Stakeholder. NWS Coordinator and Technical Partner will be available to answer local stakeholder questions as needed. | N/A | USGS has conducted stakeholder review | A | R |  |  |  |  | A | A | A |  | C
Project Management
Completed | Update Project Timeline | Update the project status in the Gantt chart in the [Timeline] tab, and inform all team members of the status of the project. | NWS and Technical Partner will update the estimate of the project tasks in the Gantt chart in the [Timeline] tab. | 2.1 |  | R | [5 empty] | A
Completed | Update the Project Development Template | Update the Project Development Template. | NWS Coordinator will update the Project Development Template. | N/A |  | R | [5 empty] | C
Completed | Obtain Status Update on AHPS Funding | Verify that AHPS Web Team has received the necessary SOW documents and the AHPS funding process is moving forward. It is critical to fund AHPS implementation prior to starting Phase 3, in order to avoid a delay. Phase 3 cannot move forward until funding has been received by AHPS Web Team . | NWS Coordinator will obtain a status update on AHPS contracting from AHPS Web Team and ensure the process is moving forward and will not delay Phase 3. | N/A | Orion has not been paid. | R |  |  |  |  | C
Phase 1 Deliverable Checklist
Project Scoping Deliverables
Completed | DRAFT STUDY AREA {study_area.shp} Format: Line shapefile (OPTIONAL) | This is the “Brown Line” on AHPS. Model extent line file shows the extent of the hydraulic model that is included within the AHPS mapping area. The study area extents should align with cross-sections on the hydraulic model, if cross-sections are available. | Technical Partner will deliver layer in (1) shapefile format, (2) in a "WGS 1984 Web Mercator (Auxillary Sphere)" projection (3) name files according to the standard-see {bracketed} example. Data will be delivered in a zip file and organized according to the [File Structure] tab. | 3.1 |  | C | [5 empty] | R |  | A
Not Applicable | DRAFT TERRAIN FOOTPRINT {terrain.shp} Format: Polygon (OPTIONAL) | A polygon outline of the terrain dataset that shows the extent of the terrain data. | Technical Partner will deliver layer in (1) shapefile format, (2) in a "WGS 1984 Web Mercator (Auxillary Sphere)" projection (3) name files according to the standard-see {bracketed} example. Data will be delivered in a zip file and organized according to the [File Structure] tab. | N/A |  | C | [5 empty] | R |  | A
Completed | DRAFT EXISTING MODEL CROSS-SECTIONS {xs.shp} Format: Line shapefile (OPTIONAL) | Include the hydraulic model cross-sections in an existing model that will be used to develop the inundation mapping. This will help the NWS Technical Coordinator to understand the extent, detail and location of an existing hydraulic model. | Technical Partner will deliver layer in (1) shapefile format, (2) in a "WGS 1984 Web Mercator (Auxillary Sphere)" projection (3) name files according to the standard-see {bracketed} example. Data will be delivered in a zip file and organized according to the [File Structure] tab. | 3.1 |  | C | [5 empty] | R |  | A
Completed | DRAFT GAGE LOCATION POINT {gage.shp} Format: Point shapefile (OPTIONAL) | The location of the stream gage data collection point. | Technical Partner will deliver layer in (1) shapefile format, (2) in a "WGS 1984 Web Mercator (Auxillary Sphere)" projection (3) name files according to the standard-see {bracketed} example. Data will be delivered in a zip file and organized according to the [File Structure] tab. | 3.1 |  | C | [5 empty] | R |  | A
Completed | DRAFT FEMA DFIRM FLOODWAY {FEMA_fldwy.shp} Format: Polygon shapefile (OPTIONAL) | The effective FEMA floodway for the study reach, clipped to the study area. | Technical Partner will deliver layer in (1) shapefile format, (2) in a "WGS 1984 Web Mercator (Auxillary Sphere)" projection (3) name files according to the standard-see {bracketed} example. Data will be delivered in a zip file and organized according to the [File Structure] tab. | 3.1 |  | C | [5 empty] | R |  | A
Completed | DRAFT FEMA DFIRM 1% {FEMA_1pct.shp} Format: Polygon shapefile (OPTIONAL) | The effective FEMA 1% annual chance floodplain (also known as the Special Flood Hazard Area) for the study reach, clipped to the study area. | Technical Partner will deliver layer in (1) shapefile format, (2) in a "WGS 1984 Web Mercator (Auxillary Sphere)" projection (3) name files according to the standard-see {bracketed} example. Data will be delivered in a zip file and organized according to the [File Structure] tab. | 3.1 |  | C | [5 empty] | R |  | A
Completed | DRAFT FEMA DFIRM 0.2% {FEMA_02pct.shp} Format: Polygon shapefile (OPTIONAL) | The effective 0.2% annual chance floodplain (if applicable) for the study reach, clipped to the study area. | Technical Partner will deliver layer in (1) shapefile format, (2) in a "WGS 1984 Web Mercator (Auxillary Sphere)" projection (3) name files according to the standard-see {bracketed} example. Data will be delivered in a zip file and organized according to the [File Structure] tab. | 3.1 |  | C | [5 empty] | R |  | A
Completed | DRAFT FLOOD CONTROL STRUCTURES {flood_cntrl.shp} Format: Line shapefile (OPTIONAL) | The centerline of a floodwall, levee or other flood control structure. Flood control structures centerlines should agree with the geographic location of the structures, as visible from satellite photography or as documented in as-built or design documents. Review the [Structures] tab in the Project Development Template and check to ensure that all flood control structures were included in the GIS data. | Technical Partner will deliver layer in (1) shapefile format, (2) in a "WGS 1984 Web Mercator (Auxillary Sphere)" projection (3) name files according to the standard-see {bracketed} example. Data will be delivered in a zip file and organized according to the [File Structure] tab. | 3.1 |  | C | [5 empty] | R |  | A
Not Applicable | DRAFT LEVEE RISK AREA {levee_ risk_area.shp} Format: Polygon Shapefile (OPTIONAL) | The identified risk area on the landward (dry) side of a levee, where flood waters would cause inundation , if the levee was to overtop. | Technical Partner will deliver layer in (1) shapefile format, (2) in a "WGS 1984 Web Mercator (Auxillary Sphere)" projection (3) name files according to the standard-see {bracketed} example. Data will be delivered in a zip file and organized according to the [File Structure] tab. | 3.1 |  | C | [5 empty] | R |  | A
Not Applicable | Draft Technical Summary Document {FIM.NWSLID.DATE.doc} (REQUIRED) | Complete Sections 1.0 "Introduction" in the Technical Summary Document. See the [Tech Doc] tab for details on report requirements. | Technical Partner will deliver a Technical Summary Document with Sections 1.0 completed. The Technical Summary Document will be formatted according to the [Tech Doc] tab. Data will be delivered in a zip file and organized according to the [File Structure] tab. Document will be delivered in MS Word format. | 3.5 | Not Required at the time this project was started. | C | [5 empty] | R | A | C
NWS Receiving Agent | Date(s) | Mandatory review at this point. This review should occur before proceeding with Phase 2A. |  |  |  | R | I | I | I | I | I | I | I | I | I | I
Kris Lander | 2011-09-08
PHASE 2A - HYDRAULIC ANALYSES | [5 empty] | Coordinator | HPM | QC Team | RFC Hydrologist | FIM Prog Mngr | AHPS Web Team | Coordinator | Hydraulic Modeler | GIS Analyst | Water Science Ctr | Local Stakeholder
Status | Task | Explanation | Actions | Guidance | Comments |  |  | NWS |  |  | NWS |  | Technical |  | USGS | Local
[11 empty] | AHPS |  | Partner
Phase 2A - Review Specifications
Not Applicable | Phase 2A Training for Technical Partners | NWS will provide detailed information to the Technical Partner on the specifications and deliverables for Phase 2A. NWS will provide training in the form of a webinar, teleconference or meeting. NWS will describe the Review Specifications for all products and summarize the requirements for the deliverable checklist. | NWS Coordinator will provide training to Technical Partner. | N/A |  | R | [5 empty] | I | I
Model Geometry Guidelines & Specifications
Completed | Model Conversion | Verify that pre-existing hydraulic model was adapted to workable FEMA approved model. | Technical Partner to develop hydraulic model and follows NWS standards. NWS will review. | 3.2.1.1 | Model Runs. 3 versions built for various flow levels. | C |  | I |  |  |  | R | A | A
Completed | Hydraulic Structures Verification | Verify that all structures published in the [Structures] tab, and identified as "Included in Hydraulic Model" are included in the model. Verify the structure geometry has been modeled at an appropriate level of detail, and includes bridge decking, piers, low chords and ineffective flow areas adjacent to structures. Create a graphic of each bridge in HEC-RAS and post the graphic to the [Structures] tab to illustrate the bridge geometry and location of low chord relative to the water surface. | Technical Partner to develop hydraulic model and follows NWS standards. Technical Partner will verify structures listed in [Structures] tab are included in the model by selecting "Yes" from "Included in Hydraulic Model?" Technical Partner will post a graphic of each bridge in the [Structures] tab. NWS will review. | 3.1.4 | All significant structures included. Minor footbridge was not included, but has not significant impact. | C |  | I |  |  |  | R | A | A
Completed | Manning's n Validation | Check the Manning's "n" values used within the model and verify the Manning's "n" values fall within the acceptable ranges published in the FHWA\USGS Standard 2339 "Guide for Selecting Manning's Roughness Coefficients for Natural Channels" | Technical Partner to develop hydraulic model and follows NWS standards. NWS will review. | N/A | Resonable n values. Friction drops north of Huntington Rd. | C |  | I |  |  |  | R | A
Completed | Downstream Boundary Conditions | Downstream boundary condition should be set to standard practices and reasonable conditions, according to the HEC-RAS manual. Backwater conditions from downstream rivers should not be used to define the boundary conditions. | Technical Partner to develop hydraulic model and follows NWS standards. NWS will review. | 3.2.1.4 |  | C |  | I |  |  |  | R | A
Not Applicable | Storage Areas (Unsteady Flow Only) | Verify that storage areas have been entered into the model and are representative of storage conditions in the field. Levees should have storage areas. This applies to unsteady flow models only. | Technical Partner to develop hydraulic model and follows NWS standards. NWS will review. | N/A | N\A | C |  | I |  |  |  | R | A
Model Results Guidelines & Specifications
Completed | FEMA FIS Profile Validation | Check agreement with FEMA Flood Insurance Study water surface profiles (if FIS is available and current) | Technical Partner to develop hydraulic model and follows NWS standards. NWS will review. | N/A | Good match. Checked all bridges. | C |  | I |  |  |  | R | A
Completed | Water Surface Elevation Validation (REQUIRED) | Plot and verify WSELs profiles agree with High Water Marks (HWM) and other historical gage data or other study data. | Technical Partner to develop hydraulic model and follows NWS standards. NWS will review. | N/A | SIM Report stated that no HWM data were used to calibrate the reach. SIM stated that 1982 era HWM data was invalid, due to levees. | C |  | I |  |  |  | R | A
Completed | Bank Full Conditions | Verify starting (lowest) elevation conveys bank full conditions. | Technical Partner to develop hydraulic model and follows NWS standards. NWS will review. | N/A | Representative of bank full conditions. | C |  | I |  |  |  | R | A
Completed | Crossing-Profiles | Incremental hydraulic model WSEL profiles should not cross | Technical Partner to develop hydraulic model and follows NWS standards. NWS will review. | N/A | Close to, but slightly higher than bank full. | C |  | I |  |  |  | R | A
Completed | Rating Curve Validation (REQUIRED) | Verify for each modeled Stage/Q, modeled Stage/Q at the AHPS gage is generally within one-half of a mapping interval of the known rating Stage/Q at the gage. The model must be calibrated to agree with the measured rating curve, at each stage\elevation target, to within 0.5 ft or 1/2 a mapping interval (whichever is less) for all stages above flood stage. | Technical Partner to develop hydraulic model and follows NWS standards. The Technical Partner will calibrate the model to agree with measured rating curve, at each stage\elevation target, to within 0.5 ft or 1/2 a mapping interval (whichever is less) for all stages above flood stage. NWS will review. | 3.2.1.2 | Good agreement within tolerances. Well documented in the technical report. | C |  | I |  |  |  | R | A
Completed | Cross-section Check | Verify HEC-RAS model cross-sections are were extended to effectively map all elevations. | Technical Partner to develop hydraulic model and follows NWS standards. NWS will review. | N/A | Minor issue in the NW corner XS 9495 to 9708 where high flows are extended to end of XS. This can be resolved by drawning the study extent line to cap the WSE boundary. Second issue noted at XS 9625 to XS 5791 is maxed out above approximately 20 ft stage. This does will not artifically raise the stage, as the stages are not above the max elevation for innefective flow area boundaries. | C |  | I |  |  |  | R | A | A
Project Management
Not Applicable | Update Project Timeline | Update the project status in the Gantt chart in the [Timeline] tab, and inform all team members of the status of the project. | NWS and Technical Partner will update the estimate of the project tasks in the Gantt chart in the [Timeline] tab. | 2.1 |  | R | [5 empty] | C
Not Applicable | Update the Project Development Template | Update the Project Development Template. | NWS Coordinator will update the Project Development Template. | N/A |  | R | [5 empty] | C
Not Applicable | Obtain Status Update on AHPS Funding | Verify that AHPS Web Team has received the necessary SOW documents and the AHPS funding process is moving forward. It is critical to fund AHPS implementation prior to starting Phase 3, in order to avoid a delay. Phase 3 cannot move forward until funding has been received by AHPS Web Team . | NWS Coordinator will obtain a status update on AHPS contracting and ensure the process is moving forward and will not delay Phase 3. | N/A |  | R |  |  |  |  | C
Phase 2A Deliverable Checklist
Hydraulic Modeling Deliverables
Not Applicable | Draft Technical Summary Document {FIM.NWSLID.DATE.doc} (REQUIRED) | Complete Sections 1.0 "Introduction" and 2.0 "Model Analysis" in the Technical Summary Document. See the [Tech Doc] tab for details on report requirements. | Technical Partner will deliver a Technical Summary Document with Sections 1.0 and 2.0 completed. The Technical Summary Document will be formatted according to the [Tech Doc] tab. Data will be delivered in a zip file and organized according to the [File Structure] tab. Document will be delivered in Adobe Acrobat .pdf format. | 3.5 |  | C |  | I |  |  |  | R | A | C
Completed | MODEL CROSS-SECTIONS {xs.shp} Format: Line shapefile (REQUIRED) | Include the hydraulic model cross-sections used to develop the inundation mapping. This will allow the NWS to evaluate the incorporation of hydraulic structures and check the width of the cross-sections. | Technical Partner will deliver layer in (1) shapefile format,(2) with FGDC compliant metadata attached by using ESRI ArcCatalog, Metadata will include elements listed in [Metadata] (3) in a "WGS 1984 Web Mercator (Auxillary Sphere)"projection (4) name files according to the standard-see {bracketed} example. Data will be delivered in a zip file and organized according to the [File Structure] tab. | 3.1 |  | C |  | I |  |  |  | R | C | A
Not Applicable | HIGH WATER MARKS {HWM.shp} Format: Point shapefile (REQUIRED) | Spatial locations of High Water Marks. High water mark elevations should be included in the shapefile table, if available. | Technical Partner will deliver layer in (1) shapefile format,(2) with FGDC compliant metadata attached by using ESRI ArcCatalog, Metadata will include elements listed in [Metadata] (3) in a "WGS 1984 Web Mercator (Auxillary Sphere)"projection (4) name files according to the standard-see {bracketed} example. Data will be delivered in a zip file and organized according to the [File Structure] tab. |  | No HWM data available.
Not Applicable | Rating Curve Extension Text File (OPTIONAL) | Create a text file that contains the rating curve. This deliverable is OPTIONAL for projects where the model was not the basis for the rating curve extension. This is required for projects where the model is the basis of the rating curve extension. | Technical Partner will deliver a text file that contains stage/flow pairs at atleast 0.5 ft intervals from a flow of 0 to the maximum flow. NWS Coordinator will deliver the rating extension to the RFC. Data will be delivered in a zip file and organized according to the [File Structure] tab. | N/A | NA | C |  | I | C |  |  | R | A
Not Applicable | PRELIMINARY FLOODPLAIN BOUNDARY {pre_elev_feet_tenth.shp} Format: Polygon shapefile (REQUIRED) | Create review-quality (post RAS / RASMapper without refinement) inundation polygons of historic events for use by reviewer(s). An inundation polygon at one elevation should be created to simulate an event where high water marks have been collected. In the absence of high water mark data, a recent FEMA DFIRM map can be used as a check. Used to check appropriate use of ineffective flow area, possible overland flow, discharge loss, etc. A depth grid of the lowest modeled stage should also be produced in order to determine if the lowest stage is representative of bankful conditions. The mapping files should be shared with the local stakeholders to validate and obtain comments on the mapping files. This is REQUIRED for all projects. | Technical Partner will create one or more inundation polygons of historic events or to match the existing DFIRM. Data will be delivered in a zip file and organized according to the [File Structure] tab. Technical Partner will create a pdf, jpeg or graphic of the map for the local stakeholders. Technical Partner will produce a depth grid of the lowest modeled stage. No metadata is required for these files. | N/A | Not applicable at the time project was scoped | C | C | C |  |  |  | R | A | A |  | C
NWS Receiving Agent | Date(s) | Mandatory review at this point for NWS Technical Partners, excluding joint USGS/NWS projects. |  |  |  | R | I | I | I | I | I | I | I | I | I | I
Kris Lander | 2012-03-21 | USGS Internal Review for joint USGS/NWS projects.
PHASE 2B - MAPPING | [5 empty] | Coordinator | HPM | QC Team | RFC Hydrologist | FIM Prog Mngr | AHPS Web Team | Coordinator | Hydraulic Modeler | GIS Analyst | Water Science Ctr | Local Stakeholder
Status | Task | Explanation | Actions | Guidance | Comments |  |  | NWS |  |  | NWS |  | Technical |  | USGS | Local
[11 empty] | AHPS |  | Partner
Phase 2B - Review Specifications
Completed | Phase 2B Training for Technical Partners | NWS will provide detailed information to the Technical Partner on the specifications and deliverables for Phase 2B. NWS will provide training in the form of a webinar, teleconference or meeting. NWS will describe the Review Specifications for all products and summarize the requirements for the deliverable checklist. | NWS Coordinator will provide training to Technical Partner. | N/A | Previously completed | R | [5 empty] | I |  | I
Completed | Calculate Final Map Display scale | Calculate the final intended map display scale based upon the underlying terrain data set DEM cell size. The map display scale will be calculated by multiplying the DEM grid cell diameter (in meters) by 2,000 pixels/meter to get the standard display scale in a standard 1 inch = X feet or 1:X ratio. The QC review will occur at the final map display scale. The final map display scale will be also be used to set the Google Maps zoom level. | NWS Coordinator will calculate the Map display scale and enter in the header of the Project Development Template. | 3.6 | 1:6,000 | R |  | I |  |  |  | I |  | I
Completed | Conduct Map Review at the Pre-determined Map Display Scale | Check Polygons and Depth Grids for visible errors at the final map display scale that was determined in Phase 2B. Errors that are visible at a scale larger than the intended map scale (i.e. zoomed in beyond the intended scale) will not require correction. NWS will check the map at the final display scale and will not zoom in beyond this display scale to review data for errors. | Technical Partner and NWS QC Team will review the depth grids for visible errors at the final map display scale. | 3.6 | Review conducted at 1:6,000 | C |  | I |  |  |  | R |  | A
Depth Grid Raster - Review Specifications
Completed | WSEL Boundary Checks | Perform reasonability check with WSEL boundary shapefiles, orthophotography, and rasters /contours. Ensure transitions along the boundary are consistent with the raster/contour data. Ensure that a terrain DEM was used to resample or downscale from a larger grid cell size to a smaller grid cell size. Ensure that the water surface is in good agreement with physical structures visible in the orthophoto, flood protection structure centerlines and other ground reference data. Verify using tools such as Google Maps and Bing Maps oblique photography. Errors should not be visible at the Final Map Display Scale. | Technical Partner will submit grid inundation layers formatted to specifications described in Project Development Template. | 3.3 |  | C |  | I |  |  |  | R |  | A
Completed | Flood Impact Evaluation | Compare inundation maps to NWS impact statements documented on AHPS and in the [Flood Impacts] tab and verify that the NWS Impact statements for the AHPS forecast point are in agreement with the inundation mapping layers. Errors should not be visible at the Final Map Display Scale. | Technical Partner will submit grid inundation layers formatted to specifications described in Project Development Template. NWS will review implacts listed in [Flood Impacts] tab and verify flood impacts are reasonable by specifying Yes or No in the field "Impact Verified in FIM Maps?" | N/A | Mike Rehbein has verified that flood impacts are valid. | C |  | I |  |  |  | R |  | A
Completed | FEMA DFIRM Agreement (OPTIONAL) | Check agreement with FEMA Flood Insurance Study DFIRM (if available and current), should reasonably agree with the corresponding grid and polygon layers. This check is OPTIONAL for projects where a DFIRM is not available or the DFIRM not be published on AHPS. | Technical Partner will submit grid inundation layers formatted to specifications described in Project Development Template. | 5.2.3.1 | Generally good agreement, except for those areas where levees have been recently installed, which resuted in | C |  | I |  |  |  | R |  | A
Completed | Bankfull Check | Ensure lowest WSEL polygon covers stream and channel banks visible from orthophotography. Errors should not be visible at the Final Map Display Scale. | Technical Partner will submit grid inundation layers formatted to specifications described in Project Development Template. | N/A | DONE | C |  | I |  |  |  | R |  | A
Completed | Higher\Lower Boundary Comparison | The boundaries of higher WSEL depth grids contain or match the boundaries of lower WSEL depth grids. Errors should not be visible at the Final Map Display Scale. The "NWS Flood Inundation Mapping Tools" GIS Toolbox contains a "Polygon Overlap QC Batch\Single" tool that should be run for each layer to identify overlaps. Polygons will need to be created prior to running the tool. | Technical Partner will submit grid inundation layers formatted to specifications described in Project Development Template. Technical Partner and NWS should use the "NWS Flood Inundation Mapping Tools" GIS Toolbox contains a "Polygon Overlap QC Batch\Single" tool . | 3.3 | DONE | C |  | I |  |  |  | R |  | A
Completed | Disconnected Wetted Areas | Remove wetted areas that result from depressions that are not hydraulically connected to the studied flow in the main river channel. Areas that are directly connected via storm sewers are acceptable. Errors should not be visible at the Final Map Display Scale. | Technical Partner will submit grid inundation layers formatted to specifications described in Project Development Template. | 3.3 | DONE | C |  | I |  |  |  | R |  | A
Completed | Dry Flood Control Structures | Verify that the impacts from all flood control structures published in the [Structures] tab are displayed per NWS specifications. Check that the depth grids are coincident with and do not overlap the levee, floodwall and temporary measures centerlines when the landward size of the structure is dry. The structures should be checked for all elevations where overtopping does not occur and for all elevations where the toe of the structure is wet, but overtopping does not occur. Errors should not be visible at the Final Map Display Scale. | Technical Partner will submit grid inundation layers formatted to specifications described in Project Development Template. | 3.3.1 |  | C |  | I |  |  |  | R |  | A
Not Applicable | Wet Flood Control Structures | Verify that the impacts from all flood control structures published in the [Structures] tab are displayed per NWS specifications. Review the impacts on the landward side of a flood control structure, after the structure overtops. 1-D Model Case: Depth grids created by a 1-D model should display a uniform and generalized risk area, on the landward side, for all elevations above the overtopping elevation. Depth values should be set to a uniform missing value. 2-D Model Case: Depth grids created by 2-D models should display unique depth grid layers, on the landward side, for each overtopped elevation. Depth values should be displayed as modeled. Errors should not be visible at the Final Map Display Scale. | Technical Partner will submit grid inundation layers formatted to specifications described in Project Development Template. | 3.3.1 | N/A | C |  | I |  |  |  | R |  | A
Completed | Bridge Decking Removal | Depth grid elevations, where the water surface is below the low chord elevation or the bridge approach, should show the depth grid as clipped in the vicnity of the bridge. The bridge should be clipped wide enough to be fully visible from an aerial photo. Extra pixels may need to be clipped from bridges that fall at angles between the cardinal directions and cross-cut the depth grids. The clipped road surface should have the value of the depth grids set to "NoData." Errors should not be visible at the Final Map Display Scale. | Technical Partner will submit grid inundation layers formatted to specifications described in Project Development Template. | 3.3.2 |  | C |  | I |  |  |  | R |  | A
Completed | Bridge Overtopping | Depth grid elevations, where the water surface is at or above the low chord elevation or the bridge approach, should cover the bridge. The depth of flow over the bridge should be representative of the total depth of flow between the water surface elevation and the elevation of the bottom of the channel. Errors should not be visible at the Final Map Display Scale. | Technical Partner will submit grid inundation layers formatted to specifications described in Project Development Template. | 3.3.2 | Per phone call with Moon on 02.22.12. NWS will be flexible with the bridge clipping on projects that were in progress. We will accept the old method (depth over road decking) for old projects but new projects should plan on following the new bridge clipping guidance. | C |  | I |  |  |  | R |  | A
Completed | Ponds, Lakes and Bodies of Water Check | Depth grid and polygons boundaries are consistent with the boundaries around ponds, lakes and other bodies of water affected by the flooding. Errors should not be visible at the Final Map Display Scale. | Technical Partner will submit grid inundation layers formatted to specifications described in Project Development Template. | N/A | DONE | C |  | I |  |  |  | R |  | A
Completed | Representative Depth Check | Depth grid raster values are reasonable and representative of the depth of flow between the modeled WSE and the terrain. Technical Partner and NWS should spot check depth measurements and review the color shaded depth grids closely. Errors should not be visible at the Final Map Display Scale. | Technical Partner will submit grid inundation layers formatted to specifications described in Project Development Template. | N/A | Depths near the gage are representative the stage at the gage. | C |  | I |  |  |  | R |  | A
Completed | Positive Depth Check | Ensure that wetted areas have positive depths and non-wetted area depths are set to "NoData" values. | Technical Partner will submit grid inundation layers formatted to specifications described in Project Development Template. | N/A | DONE | C |  | I |  |  |  | R |  | A
Inundation Polygon - Review Specifications
Completed | Polygon & Grid Pairing | Ensure there is a corresponding depth grid raster file(s) for each Inundation polygon file(s). | Technical Partner will submit polygon and grid inundation layers formatted to specifications described in Project Development Template Description. | N/A | DONE | C |  | I |  |  |  | R |  | A
Completed | Polygon & Grid Consistency | Each polygon will be an exact copy of the depth grid. Polygons should not be smoothed or interpolated to remove the jagged or rectilinear edges. | Technical Partner will submit polygon and grid inundation layers formatted to specifications described in Project Development Template Description. Technical Partner and NWS should use the "NWS Flood Inundation Mapping Tools" in the GIS Toolbox contains to verify that the Polygons and Grids are an exact match. | N/A | Polygon Grid QC turned up a lot of small polygons, but none of significance. | C |  | I |  |  |  | R |  | A
Mapping File Management - Review Specifications
Completed | Projection | Set the coordinate system for shapefiles and rasters to "WGS 1984 Web Mercator (Auxillary Sphere)" | Technical Partner will submit all GIS layers projected to a "WGS 1984 Web Mercator (Auxillary Sphere)" projection. | ESRI | DONE | C |  | I |  |  |  | R |  | A
Completed | Naming Convention | Verify that file naming convention used for base mapping data, inundation polygons and depth rasters layers conforms to required naming conventions. Naming conventions are identified by the {bracketed names.shp} present in the Final Deliverables Check List. | Technical Partner will submit GIS layers formatted to the naming specifications described in for each deliverable. | N/A | DONE | C |  | I |  |  |  | R |  | A
Completed | Metadata | Review and verify that metadata is attached to all GIS data and meets FGDC standards. Enter metadata using the ESRI ArcCatalog application. Verify that the metadata fields and text that are published in the [Metadata] tab have been added to the corresponding data set. | Technical Partner will create new metadata or verify that existing metadata is attached to all GIS data and meets FGDC standards. Partner will enter and attach metadata to the shapefiles and grids using the ESRI ArcCatalog application. Metadata will include elements listed in the [Metadata] tab. NWS QC Team will review every item on the [Metadata] tab to verify metadata has been submitted. | 3.1.9 |  | C |  | I |  |  |  | R |  | A
Completed | File Structure | Each deliverable will be submitted and organized according to a standard file structure and naming convention outlined in the [File Structure] tab. | Technical Partner will format deliverable according to the [File Structure] tab. | N/A | DONE | C |  | I |  |  |  | R | A | A
Project Management
Not Applicable | Update Project Timeline | Update the project status in the Gantt chart in the [Timeline] tab, and inform all team members of the status of the project. | NWS and Technical Partner will update the estimate of the project tasks in the Gantt chart in the [Timeline] tab. | 2.1 |  | R | [5 empty] | C
Completed | Update the Project Development Template | Update the Project Development Template. | NWS Coordinator will update the Project Development Template. | N/A |  | R | [5 empty] | C
Not Started | Verify AHPS Funding Received | Verify that AHPS Web Team has received AHPS funding. Phase 3 activities cannot begin until funding has been received. | NWS Coordinator will coordinate with AHPS Web Team and the funding source to verify that funding has been sent and received prior to starting Phase 3. | N/A | AHPS FUNDING HAS NOT BEEN RECEIVED. Project cannot be published on AHPS (Phase 3) untill Ortion Techologies recieves funding. | R |  |  |  |  | C
Phase 2B Deliverable Checklist
GIS Data Deliverables
In Progress | STUDY AREA {study_area.shp} Format: Line shapefile (REQUIRED) | This is the “Brown Line” on AHPS. Model extent line file shows the extent of the hydraulic model that is included within the AHPS mapping area. The study area extents should align with cross-sections on the hydraulic model. | Technical Partner will deliver layer in (1) shapefile format,(2) with FGDC compliant metadata attached by using ESRI ArcCatalog, Metadata will include elements listed in [Metadata] (3) in a "WGS 1984 Web Mercator (Auxillary Sphere)" projection (4) name files according to the standard-see {bracketed} example. Data will be delivered in a zip file and organized according to the [File Structure] tab. | 3.1 | Additional Study Area extent line should be drawn in the NW corner to show that water is not transferred to the next project basin. Without this constrain, water depth transition from 2-4 ft to zero ft. See QC shapefile. DONE. | C |  | A |  |  |  | R |  | A
Completed | MODEL CROSS-SECTIONS {xs.shp} Format: Line shapefile (REQUIRED) | Include the hydraulic model cross-sections used to develop the inundation mapping. This will allow the modeling to be archived for future applications and updates to the inundation mapping. | Technical Partner will deliver layer in (1) shapefile format,(2) with FGDC compliant metadata attached by using ESRI ArcCatalog, Metadata will include elements listed in [Metadata] (3) in a "WGS 1984 Web Mercator (Auxillary Sphere)" projection (4) name files according to the standard-see {bracketed} example. Data will be delivered in a zip file and organized according to the [File Structure] tab. | 3.1 |  | C |  | A |  |  |  | R |  | A
Completed | GAGE LOCATION POINT {gage.shp} Format: Point shapefile (REQUIRED) | The location of the stream gage data collection point. | Technical Partner will deliver layer in (1) shapefile format,(2) with FGDC compliant metadata attached by using ESRI ArcCatalog, Metadata will include elements listed in [Metadata] (3) in a "WGS 1984 Web Mercator (Auxillary Sphere)" projection (4) name files according to the standard-see {bracketed} example. Data will be delivered in a zip file and organized according to the [File Structure] tab. | 3.1 |  | C |  | A |  |  |  | R |  | A
Not Applicable | FEMA DFIRM FLOODWAY {FEMA_fldwy.shp} Format: Polygon shapefile (OPTIONAL) | The effective FEMA floodway for the study reach, clipped to the study area. | Technical Partner will deliver layer in (1) shapefile format,(2) with FGDC compliant metadata attached by using ESRI ArcCatalog, Metadata will include elements listed in [Metadata] (3) in a "WGS 1984 Web Mercator (Auxillary Sphere)" projection (4) name files according to the standard-see {bracketed} example. Data will be delivered in a zip file and organized according to the [File Structure] tab. | 3.1 | Delete the "optional_dfirm" folder and remove zip file for final submittal. DONE. | C |  | A |  |  |  | R |  | A
Not Applicable | FEMA DFIRM 1% {FEMA_1pct.shp} Format: Polygon shapefile (OPTIONAL) | The effective FEMA 1% annual chance floodplain (also known as the Special Flood Hazard Area) for the study reach, clipped to the study area. | Technical Partner will deliver layer in (1) shapefile format,(2) with FGDC compliant metadata attached by using ESRI ArcCatalog, Metadata will include elements listed in [Metadata] (3) in a "WGS 1984 Web Mercator (Auxillary Sphere)" projection (4) name files according to the standard-see {bracketed} example. Data will be delivered in a zip file and organized according to the [File Structure] tab. | 3.1 |  | C |  | A |  |  |  | R |  | A
Not Applicable | FEMA DFIRM 0.2% {FEMA_02pct.shp} Format: Polygon shapefile (OPTIONAL) | The effective 0.2% annual chance floodplain (if applicable) for the study reach, clipped to the study area. | Technical Partner will deliver layer in (1) shapefile format,(2) with FGDC compliant metadata attached by using ESRI ArcCatalog, Metadata will include elements listed in [Metadata] (3) in a "WGS 1984 Web Mercator (Auxillary Sphere)" projection (4) name files according to the standard-see {bracketed} example. Data will be delivered in a zip file and organized according to the [File Structure] tab. | 3.1 |  | C |  | A |  |  |  | R |  | A
Completed | FLOOD CONTROL STRUCTURES {flood_cntrl.shp} Format: Line shapefile (OPTIONAL) | The centerline of a floodwall, levee or other flood control structure. Flood control structures centerlines should agree with the geographic location of the structures, as visible from satellite photography or as documented in as-built or design documents. Review the [Structures] tab in the Project Development Template and check to ensure that all flood control structures were included in the GIS data. | Technical Partner will deliver layer in (1) shapefile format,(2) with FGDC compliant metadata attached by using ESRI ArcCatalog, Metadata will include elements listed in [Metadata] (3) in a "WGS 1984 Web Mercator (Auxillary Sphere)" projection (4) name files according to the standard-see {bracketed} example. Data will be delivered in a zip file and organized according to the [File Structure] tab. | 3.1 |  | C |  | A |  |  |  | R |  | A
Not Applicable | LEVEE RISK AREA {levee_ risk_area.shp} Format: Polygon Shapefile (OPTIONAL) | The identified risk area on the landward (dry) side of a levee, where flood waters would cause inundation , if the levee was to overtop. | Technical Partner will deliver layer in (1) shapefile format,(2) with FGDC compliant metadata attached by using ESRI ArcCatalog, Metadata will include elements listed in [Metadata] (3) in a "WGS 1984 Web Mercator (Auxillary Sphere)" projection (4) name files according to the standard-see {bracketed} example. Data will be delivered in a zip file and organized according to the [File Structure] tab. | 3.1 | NA | C |  | A |  |  |  | R |  | A
In Progress | DEPTH GRIDS {elev_feet_tenth} Format: ESRI Grid (REQUIRED) | Depth grids corresponding to mapped inundation areas from action stage through at least the flood of record at 1 ft intervals or less. For example, a depth grid with a water surface elevation of 78.3 feet NAVD88 at the gage would be named “elev_78_3”. Each depth grid should include the appropriate support files, with extensions # dblbnd.adf, # hdr.adf, # sta.adf; # vat.adf; #w001001.adf; # w001001x.adf | Technical Partner will deliver layer in (1) ESRI Grid format,(2) with FGDC compliant metadata attached by using ESRI ArcCatalog, Metadata will include elements listed in [Metadata] (3) in a "WGS 1984 Web Mercator (Auxillary Sphere)" projection (4) name files according to the standard-see {bracketed} example. Data will be delivered in a zip file and organized according to the [File Structure] tab. | N/A | Data were delivered unprojected. Projection needs to be WGS 1984 Web Mercator (Auxillary Sphere). DONE. | C |  | A |  |  |  | R | A | A
Completed | POLYGONS {elev_feet_tenth.shp} Format: Polygon shapefile (REQUIRED) | Mapped inundation areas from action stage through at least the flood of record at 1 ft intervals or less. For example, an inundation area with a water surface elevation of 78.3 feet NAVD88 at the gage would be named “elev_78_3.shp”. Each mapped inundation area should include the following file extensions: .dbf, .prj, .sbn, .sbx, .shp, .shp, .xml, and .shx. | Technical Partner will deliver layer in (1) shapefile format,(2) with FGDC compliant metadata attached by using ESRI ArcCatalog, Metadata will include elements listed in [Metadata] (3) in a "WGS 1984 Web Mercator (Auxillary Sphere)"projection (4) name files according to the standard-see {bracketed} example. Data will be delivered in a zip file and organized according to the [File Structure] tab. | N/A |  | C |  | A |  |  |  | R | A | A
Project Documentation Deliverables
Completed | Terrain Data (OPTIONAL) | The terrain DEM that was used to process the original data. Terrain data should have metadata associated. | Technical Partner to provide terrain data. Terrain data are provided outside of zip file. See [File Structure]. | 3.1.6 | Terrain data was submitted. | I | [5 empty] | R | A | A
Completed | Hydraulic Model (REQUIRED) | Include hydraulic model data (as digital files). | Technical Partner to provide hydraulic model that has passed NWS QAQC review. Model to be provided according to [File Structure] | N/A |  | I | [5 empty] | R | A
Completed | Final Technical Summary Document - Hydraulics & GIS {FIM.NWSLID.DATE.doc} (REQUIRED) | Include completed Technical Summary document with Sections 1.0, 2.0, 3.0 and 4.0 completed as specified in the [Tech Doc] tab. | Technical Partner to provide Technical Summary Document that has passed NWS QAQC review. The Technical Summary Document will be formatted according to the [Tech Doc] tab. Data will be delivered in a zip file and organized according to the [File Structure] tab. Document will be delivered in Adobe Acrobat .pdf format. | 3.5 | Format is similar to the Tech Doc | I | [5 empty] | R | A | A
NWS Receiving Agent | Date | Confirm data are received by NWS. Technical Partner obligation is completed. |  |  |  | R | I | I | I | I | I | I | I | I | I | I
PHASE 3 - AHPS WEB IMPLEMENTATION | [5 empty] | Coordinator | HPM | QC Team | RFC Hydrologist | FIM Prog Mngr | AHPS Web Team | Coordinator | Hydraulic Modeler | GIS Analyst | Water Science Ctr | Local Stakeholder
Status | Task | Explanation | Actions | Guidance | Comments |  |  | NWS |  |  | NWS |  | Technical |  | USGS | Local
[11 empty] | AHPS |  | Partner
Beta Map Review Checklist Items
| Map Display Scale | Ensure that the AHPS Google Zoom level has been adjusted so that the user cannot zoom beyond the final map display scale specified in the project development template. A Google zoom level reference table is available in the [Spatial Calc] tab. | NWS Coordinator will use the provide AHPS Web Team with the final display scale associated Google Zoom Level. | 3.6 |  | R |  | A |  |  | A | C
| Overall Accuracy in AHPS format | Ensure that all GIS layers that have been checked in are present and displayed properly on AHPS. | NWS and Technical Partner will review the AHPS Beta site | N/A |  | R | A | A |  |  | A | C
| Partnership Acknowledgements | Verify the AHPS page acknowledges the partnerships that participated in the funding of AHPS implementation and in the development of the inundation mapping layers. | NWS and Technical Partner will review the AHPS Beta site | N/A |  | R | A |  |  |  | A | C
| Map Disclaimer | Review the standard AHPS project map disclaimer. Determine if there is a need to add a project specific map disclaimer in the "Site-specific information" section on AHPS. If temporary measures are placed, caveat the AHPS page to display the limitation of the modeling, which would not include temporary measures. | NWS and Technical Partner will review the AHPS Beta site and collaborate on a project specific disclaimer, if required. | N/A |  | R | A |  |  |  | A | C
Review
| NWS Internal Review | Beta Review: NWS Staff involved with the proejct, will review the final AHPS map during the Beta Review period. | NWS Coordinator, HPM, QC Team, RFC Hydrologist, and FIM Program Manager will review the AHPS map. | N/A |  | R | A | A | A | A | I
| Technical Partner Review | Beta Review: Technical Partner will review AHPS Beta Site and provide comments after the Beta Map Review has been conducted. | Technical Partner will review and provide comments to NWS Coordinator. NWS Coordinator will provide comments to AHPS Web Team. | N/A |  | R |  |  |  |  | I | A | A | A
| Local Stakeholder Final Review | Post-Beta Review: Contact local stakeholders and invite them to review and comment on the final AHPS product. Provide local stakeholders with 30 days to review and provide comments. | NWS HPM will contact the Local Stakeholders and coordinate a Final Stakeholder Rview. Local Stakeholder will review and provide comments to NWS HPM. NWS HPM will provide comments to NWS Coordinator and AHPS Web Team. | N/A |  | A | R |  |  |  | I |  |  |  |  | C
Map Launch Event
| Local Outreach Event (OPTIONAL) | NWS and Local Stakeholders may plan a public outreach event and launch of the mapping product in the local community. This event is OPTIONAL. | NWS HPM will work with the Local Stakeholder to develop a public outreach event. | N/A |  | C | R |  |  | I |  | C |  |  |  | C
Project Management
| Update the Project Development Template | Update the Project Development Template. | NWS Coordinator will update the Project Development Template and coordinate with the Technical Partner on any oustanding issues. | N/A |  | R | [5 empty] | C
| Add Project Development Template to Final Deliverable ZIP file | A copy of the final Project Development Template should be provided to the public, via AHPS Web. | NWS Coordinator will add the final and completed copy of the Project Development Template to the ZIP file that will be hosted on AHPS. This should be completed after completing and signing off on Phase 3. | N/A |  | R
| Project Closeout | Projects should be closed out and archived. The data may be needed at a future date, and NWS should not rely on AHPS as a backup system for hosting the FIM studies. Project shold also be archived in case there are future request for project documentation that is not avialable on the AHPS web. Any HEC-RAS or other hydraulic models should be provided to the RFCs. Project documents should be organized according to the [File Structure] tab. | NWS Coordinator will organize and consolidate all project deliverables, working files and project documentation according to the [File Structure] tab. NWS Coordinator will burn 2 DVDs of all project data. I copy will be kept at the Regional HQ and 1 copy will be shipped to the FIM Program Manager at NWSHQ. | N/A |  | R |  |  |  | C
Project Documentation Deliverables
| Final Project Development Template {FIM.NWSLID.DATE.xls} (REQUIRED) | Submit the Final Project Development Template for archive to close out the project. | NWS Coordinator will archive a copy of the Project Development template as a part of the closeout process. | N/A |  | R
NWS Receiving Agent | Date | Confirm AHPS page is acceptable to Technical Partner Coordinator, NWS Coordinator, and Local Stakeholders. |  |  |  | R | I | I | I | I | C | I | I | I | I | I
AHPS Contractor obligation is completed.
| Status List | Work List
| Not Started | R
| In Progress | A
| Completed | C
| Not Applicable | I

## Timeline
Project Timeline
Phase | Start date (mm/dd/yyyy) | End date (mm/dd/yyyy) | Percent Complete | Duration (days) | Completed (days) | Remaining (days)
PHASE 1- PROJECT SCOPING AND PLANNING | 2012-01-01 | 2012-03-01 | 74.8% | 61 | 45.626 | 15.374
Pre-Scoping & Planning Activities | 2012-01-01 | 2012-02-01 | 100% | 32 | 32 | 0
Site Selection & Evaluation Scoping | 2012-02-01 | 2012-03-01 | 100% | 30 | 30 | 0
Hydraulic Model Scoping | 2012-02-01 | 2012-03-01 | 100% | 30 | 30 | 0
GIS Product Scoping | 2012-02-01 | 2012-03-01 | 0% | 30 | 0 | 30
<<Phase 1 Review>> | 2012-03-01 | 2012-03-01 | 0% | 1 | 0 | 1
PHASE 2A - HYDRAULIC ANALYSIS | 2012-03-01 | 2012-06-01 | 0% | 93 | 0 | 93
Hydraulic Model Development by Partner | 2012-03-01 | 2012-05-15 | 0% | 76 | 0 | 76
Hydraulic Model Review by NWS | 2012-05-15 | 2012-06-01 | 0% | 18 | 0 | 18
<<Phase 2A Review>> | 2012-06-01 | 2012-06-01 | 0% | 1 | 0 | 1
PHASE 2B - MAPPING | 2012-06-01 | 2012-10-01 | 0% | 123 | 0 | 123
Mapping Product Development by Partner | 2012-06-01 | 2012-10-01 | 0% | 123 | 0 | 123
Mapping Product Review by NWS | 2012-07-01 | 2012-10-01 | 0% | 93 | 0 | 93
<<Phase 2B Review>> | 2012-10-01 | 2012-10-01 | 0% | 1 | 0 | 1
PHASE 3 - AHPS WEB IMPLEMENTATION | 2012-10-01 | 2012-12-01 | 0% | 62 | 0 | 62
AHPS Beta Site Development | 2012-10-01 | 2012-11-01 | 0% | 32 | 0 | 32
AHPS Beta Map Review | 2012-11-01 | 2012-12-01 | 0% | 31 | 0 | 31
<<Phase 3 Review>> | 2012-12-01 | 2012-12-01 | 0% | 1 | 0 | 1
Formulas:
Start date (mm/dd/yyyy) = MIN([Start date (mm/dd/yyyy), row below]:B9)
End date (mm/dd/yyyy) = MAX([End date (mm/dd/yyyy), row below]:C9)
End date (mm/dd/yyyy) = [Start date (mm/dd/yyyy)]

## Location Map
Location Map Graphics
| USGS Gage Location Map: (Note: same as report Figure 1) |  |  | AHPS Gage Location Map:
| Insert USGS Gage Location Map |  |  | Insert AHPS Gage Location Map
|  | Example: | http://waterdata.usgs.gov/ia/nwis/nwismap/?site_no=05454500&agency_cd=USGS |  | http://water.weather.gov/ahps2/hydrograph.php?wfo=dvn&gage=iowi4&view=1,1,1,1,1,1,1,1
Use standard Google "Map" background
Overview Map: (Note: same as report Figure 2)
Layers:
Stream Gage(s) Location
Study Extent Boundary
Base Map:
aerial photo, roads, corporate boundaries, county boundaries
Impacts Map:
Layers:
Stream Gage Location
Study Extent Boundary
Location of Flood Impacts
Location of flood Control Structures
Location of Temporary measures
Model cross-sections
FEMA DFIRM
Base Map:
Aerial background map with roads

## Flood Impacts
Flood Impacts
Stage | Elevation | Location Description | Impact Description | Impact Verified | Flood History
(ft) | NAVD88 (ft) | (River Miles U/S or D/S from gage) |  | In FIM Maps?
22 | 770.46 |  | Structural damage is done to homes and businesses on the south side of Fort Wayne near the Saint Mary's River. Record flood was set on July 9, 2003 when the river reached 21.2 feet. |  | (1) 21.20 ft on 07/09/2003
20 | 768.46 | ? | A major flood is in progress and water is nearing the top of many levees. When the Muldoon Bridge gage reads 20.3 feet, the flood becomes a 100 year event. |  | (2) 19.66 ft on 03/14/1982
19 | 767.46 | ? | Flooding reaching major category with extensive evacuations becoming necessary. Primary roads and bridges are closed at this level. |  | (3) 19.06 ft on 01/14/2005
18 | 766.46 | ? | An increasing number of city streets flood...and more evacuations become necessary. Property damage approaches severe category in some areas at this level. |  | (4) 18.33 ft on 02/26/1985
17 | 765.46 |  | Some residents in the Winchester Road area and Fairwick Apartments may need to be evacuated. Property damage increases in some areas at this level. |  | (5) 17.92 ft on 01/01/1991
15 | 763.46 | ? | Flooding occurs on the lowest unprotected city streets, park drives and county roads. |  | (6) 17.67 ft on 02/09/2008
14 | 762.46 | ? | Flooding occurs in parks and low farmland throughout southern Allen County. The City of Fort Wayne starts 24 hour flood fighting procedures. |  | (7) 17.07 ft on 07/18/1992
(8) 17.03 ft on 01/26/1999
(9) 16.98 ft on 03/11/2009
(10) 16.32 ft on 03/03/2011
(11) 16.06 ft on 02/13/2009
(12) 15.81 ft on 05/12/2003
(13) 15.48 ft on 06/14/2004
(14) 15.23 ft on 01/07/2005
(15) 15.00 ft on 12/04/2011
(16) 14.73 ft on 05/26/2011
(17) 14.62 ft on 01/17/2007
(18) 14.34 ft on 04/14/1994
(19) 13.96 ft on 08/06/2003
(20) 13.49 ft on 04/01/2002
(21) 12.78 ft on 01/06/2004
(22) 12.32 ft on 02/01/2002
(23) 11.87 ft on 12/31/2005
(24) 11.78 ft on 02/10/2001
(25) 11.26 ft on 12/02/2006
(26) 11.17 ft on 10/17/2001
(27) 9.59 ft on 10/26/2001
(28) 9.36 ft on 05/14/2002

## Rating
Rating Curve Comparison Worksheet
# //UNITED STATES GEOLOGICAL SURVEY http://water.usgs.gov/
NWS Rating Curve Link: |  |  | (NWS AHPS XML rating is intended for initial comparison only. You must obtain the official rating for the RFC, AHPS Rating may not be current\correct) | [9 empty] | # //NATIONAL WATER INFORMATION SYSTEM http://water.usgs.gov/data.html
|  |  | (replace NWSLID with the 5 letter ID for the AHPS gage. Look for XML tag <rating dignity="official"> ) | [9 empty] | # //DATA ARE PROVISIONAL AND SUBJECT TO CHANGE UNTIL PUBLISHED BY USGS
| NWS AHPS XML Rating |  |  |  | http://water.weather.gov/ahps2/hydrograph_to_xml.php?gage=mtzi3&output=xml | [7 empty] | # //RETRIEVED: 2012-03-13 20:46:46
# //WARNING
USGS Rating Depot Link: |  |  | (replace XXXXXXXX gage ID with the 8-15 digit USGS station number) | [9 empty] | # //WARNING The stage-discharge rating provided in this file should be
| List of Available Rating Products |  |  |  | http://waterdata.usgs.gov/nwisweb/cgi-src/get_ratings?site_no=XXXXXXXX | [7 empty] | # //WARNING considered provisional and subject to change. Stage-discharge
| **Expanded Shift Adjusted Rating (exsa) |  |  |  | http://waterdata.usgs.gov/nwisweb/data/ratings/exsa/USGS.XXXXXXXX.exsa.rdb | [7 empty] | # //WARNING ratings change over time as the channel features that control
| Base Rating (base) |  |  |  | http://waterdata.usgs.gov/nwisweb/data/ratings/base/USGS.XXXXXXXX.base.rdb | [7 empty] | # //WARNING the relation between stage and discharge vary. Users are
| Corrections (corr) |  |  |  | http://waterdata.usgs.gov/nwisweb/data/ratings/corr/USGS.XXXXXXXX.corr.rdb | [7 empty] | # //WARNING cautioned to consider carefully the applicability of this
| ** Use the expanded shift adjusted rating in the table below. Other links are for reference only. | [11 empty] | # //WARNING rating before using it for decisions that concern personal or
# //WARNING public safety or operational consequences.
FEMA FIS | (obtain the Flood Insurance Report. Turn to the "Hydrologic Analyses" section | [7 empty] | FEMA: St. Marys River Just downstrem of confluence of Paul Trier Ditch |  |  |  | # //WARNING
| Federal Agencies |  |  |  | http://edd.msc.fema.gov/edd/ | [5 empty] | 10300 | 10% | # //FILE TYPE="NWIS RATING"
| Non-Federal Partners |  |  |  | https://msc.fema.gov | [5 empty] | 15700 | 1% | # //DATABASE NUMBER=1 DESCRIPTION=" Standard data base for this site."
[9 empty] | F |  |  |  | # //STATION AGENCY="USGS " NUMBER="04182000 " TIME_ZONE="EST" DST_FLAG=N
Date Created: | [12 empty] | # //STATION NAME="ST. MARYS RIVER NEAR FORT WAYNE, IN"
Date Aquired: | 03.20.12 | [11 empty] | # //DD NUMBER=" 2" LABEL="Discharge (cfs)" | DEF-RC
| USGS | USGS | NWS RFC | NWS RFC | FEMA FIS | FEMA FIS | Model | Model |  |  |  |  | # //PARAMETER CODE="00060" | ID SASI3 REPL
| Stage (ft) | Flow (cfs) | Stage (ft) | Flow (cfs) | Stage (ft) | Flow (cfs) | Stage (ft) | Flow (cfs) |  |  |  |  | # //RATING SHIFTED="20120313200000 EST" | 'NEAR FORT WAYNE, IN ' 'ST. MARYS RIVER ' 40.98 85.10
| 0.5 | 3.7 | 0.71 | 3.7 | 17.04 | 10300 | [6 empty] | # //RATING ID="32.0" TYPE="STGQ" NAME="stage-discharge" AGING=A | E 48 0 762.00 141.00 INT=LOG RR=FLUD
| 1 | 36 | 1 | 19 | 20.54 | 15700 | 12.2638 | 5370 |  |  |  |  | # //RATING REMARKS="Extended RT # 31 at the high-end" | 14.00 748.97 0.71 'WS= 12.'
| 2 | 177 | 2 | 139 |  |  | 13.2323 | 6160 |  |  |  |  | # //RATING EXPANSION="logarithmic" | 0.71 3.70 0.80 7.20 1.00 19.00
| 3 | 408 | 3 | 358 |  |  | 14.0962 | 7000 |  |  |  |  | # //RATING OFFSET1=0.30 | 1.20 35.00 1.40 55.00 1.60 79.00
| 4 | 722 | 4 | 660 |  |  | 14.8557 | 7880 |  |  |  |  | # //RATING_INDEP ROUNDING="2223456782" PARAMETER="Gage height (ft)" | 1.80 107.00 2.00 139.00 2.20 175.00
| 5 | 1110 | 5 | 1040 |  |  | 15.5712 | 8800 |  |  |  |  | # //RATING_DEP ROUNDING="2222233332" PARAMETER="Discharge (cfs)" | 2.40 216.00 2.60 259.00 2.80 306.00
| 6 | 1580 | 6 | 1510 |  |  | 17.4349 | 9760 |  |  |  |  | # //RATING_DATETIME BEGIN=20021001000100 BZONE=EST END=20101012235959 EZONE=EST AGING=A | 3.00 358.00 3.20 411.00 3.40 468.00
| 7 | 2100 | 7 | 2040 |  |  | 18.0962 | 10800 |  |  |  |  | # //RATING_DATETIME BEGIN=20101013000000 BZONE=EST END=20111004235959 EZONE=EST AGING=R | 3.60 530.00 3.80 593.00 4.00 660.00
| 8 | 2660 | 8 | 2600 |  |  | 18.801 | 12000 |  |  |  |  | # //RATING_DATETIME BEGIN=20111005000000 BZONE=EST END=23821230190000 EZONE=EST AGING=W | 4.20 732.00 4.40 805.00 4.60 884.00
| 9 | 3260 | 9 | 3220 |  |  | 20.0156 | 13300 |  |  |  |  | # //SHIFT_PREV BEGIN="20111005131500" BZONE="EST" END="--------------" EZONE="---" | 4.80 963.00 5.00 1040.00 5.50 1270.00
| 10 | 3920 | 10 | 3870 |  |  | 20.775 | 14700 |  |  |  |  | # //SHIFT_PREV STAGE1="0.50" SHIFT1="0.00" STAGE2="2.00" SHIFT2="0.00" STAGE3="7.00" SHIFT3="0.00" | 6.00 1510.00 6.50 1760.00 7.00 2040.00
| 11 | 4620 | 11 | 4580 |  |  | 21.6903 | 16200 |  |  |  |  | # //SHIFT_PREV COMMENT=" " | 7.50 2310.00 8.00 2600.00 8.50 2890.00
| 12 | 5370 | 12 | 5340 | [8 empty] | # //SHIFT_NEXT BEGIN="--------------" BZONE="---" END="--------------" EZONE="---" | 9.00 3200.00 9.50 3530.00 10.00 3870.00
| 13 | 6160 | 13 | 6140 | [8 empty] | # //SHIFT_NEXT STAGE1="---" SHIFT1="---" STAGE2="---" SHIFT2="---" STAGE3="---" SHIFT3="---" | 10.50 4220.00 11.00 4580.00 12.00 5340.00
| 14 | 7000 | 14 | 7000 | [8 empty] | # //SHIFT_NEXT COMMENT=" " | 13.00 6140.00 14.00 7000.00 15.00 7880.00
| 15 | 7880 | 15 | 7880 | [8 empty] | INDEP SHIFT DEP STOR | 16.00 8800.00 17.00 9760.00 18.00 10800.00
| 16 | 8800 | 16 | 8800 | [8 empty] | 16N 16N 16N 1S | 19.00 12000.00 20.00 13300.00 21.00 14700.00
| 17 | 9760 | 17 | 9760 | [8 empty] | 0.50 0.00 3.7 * | 22.00 16200.00 23.00 17700.00 23.30 18200.00
| 18 | 10800 | 18 | 10800 | [8 empty] | 0.51 0.00 4.0 | USGS-ID '04182000'
| 19 | 12000 | 19 | 12000 | [8 empty] | 0.52 0.00 4.4 | COMMENT &
| 20 | 13300 | 20 | 13300 | [8 empty] | 0.53 0.00 4.8 | 'USGS RATING #32 (2009). Shifted 20101020. '
| 21 | 14700 | 21 | 14700 | [8 empty] | 0.54 0.00 5.1 | END
| 22 | 16200 | 22 | 16200 | [8 empty] | 0.55 0.00 5.5 | STOP
| 23 | 17700 | 23 | 17700 | [8 empty] | 0.56 0.00 5.9
| 23.3 | 18200 | 23.3 | 18200 | [8 empty] | 0.57 0.00 6.4
0.58 0.00 6.8
0.59 0.00 7.2
0.60 0.00 7.7
0.61 0.00 8.2
0.62 0.00 8.7
0.63 0.00 9.1
0.64 0.00 9.7
0.65 0.00 10
0.66 0.00 11
0.67 0.00 11
0.68 0.00 12
0.69 0.00 12
0.70 0.00 13
0.71 0.00 14
[9 empty] | 20-22 ft |  |  |  | 0.72 0.00 14
[9 empty] | Line Style | Variable=WS1, Line Style=1, Line Color=7, Line Width=0.5, Sym Type=0, Sym Color=7, Sym Size=3, Polygon=0, FillMode=1, FillColor=0, On Bottom(in legend)=False, Sort (in legend)=-1, Legend Only=0 |  |  | 0.73 0.00 15
[9 empty] | Label | W.S. Elev |  |  | 0.74 0.00 15
[9 empty] | x | y |  |  | 0.75 0.00 16
[9 empty] | 0 | 745.58 | -2.88 |  | 0.76 0.00 17
[9 empty] | 13300 | 768.4756 | 20.0156 |  | 0.77 0.00 17
[9 empty] | 14700 | 769.235 | 20.775 |  | 0.78 0.00 18
[9 empty] | 16200 | 770.1503 | 21.6903 |  | 0.79 0.00 19
0.80 0.00 19
[9 empty] | 17-19 ft |  |  |  | 0.81 0.00 20
[9 empty] | Line Style | Variable=WS1, Line Style=1, Line Color=7, Line Width=0.5, Sym Type=0, Sym Color=7, Sym Size=3, Polygon=0, FillMode=1, FillColor=0, On Bottom(in legend)=False, Sort (in legend)=-1, Legend Only=0 |  |  | 0.82 0.00 21
[9 empty] | Label | W.S. Elev |  |  | 0.83 0.00 22
[9 empty] | x | y |  |  | 0.84 0.00 22
[9 empty] | 0 | 745.3 | -3.16 |  | 0.85 0.00 23
[9 empty] | 9760 | 765.8949 | 17.4349 |  | 0.86 0.00 24
[9 empty] | 10800 | 766.5562 | 18.0962 |  | 0.87 0.00 25
[9 empty] | 12000 | 767.261 | 18.801 |  | 0.88 0.00 25
0.89 0.00 26
[9 empty] | 12-16 ft |  |  |  | 0.90 0.00 27
[9 empty] | Line Style | Variable=WS1, Line Style=1, Line Color=7, Line Width=0.5, Sym Type=0, Sym Color=7, Sym Size=3, Polygon=0, FillMode=1, FillColor=0, On Bottom(in legend)=False, Sort (in legend)=-1, Legend Only=0 |  |  | 0.91 0.00 28
[9 empty] | Label | W.S. Elev |  |  | 0.92 0.00 29
[9 empty] | x | y |  |  | 0.93 0.00 29
[9 empty] | 0 | 745.3 | -3.16 |  | 0.94 0.00 30
[9 empty] | 5370 | 760.7728 | 12.3128 |  | 0.95 0.00 31
[9 empty] | 6160 | 761.7459 | 13.2859 |  | 0.96 0.00 32
[9 empty] | 7000 | 762.6219 | 14.1619 |  | 0.97 0.00 33
[9 empty] | 7880 | 763.3858 | 14.9258 |  | 0.98 0.00 34
[9 empty] | 8800 | 764.0969 | 15.6369 |  | 0.99 0.00 35
1.00 0.00 36
1.01 0.00 37
1.02 0.00 37
1.03 0.00 38
1.04 0.00 39
1.05 0.00 40
1.06 0.00 41
1.07 0.00 42
1.08 0.00 43
1.09 0.00 44
1.10 0.00 45
1.11 0.00 46
1.12 0.00 47
1.13 0.00 48
1.14 0.00 50
1.15 0.00 51
1.16 0.00 52
1.17 0.00 53
1.18 0.00 54
1.19 0.00 55
1.20 0.00 56
1.21 0.00 57
1.22 0.00 58
1.23 0.00 59
1.24 0.00 61
1.25 0.00 62
1.26 0.00 63
1.27 0.00 64
1.28 0.00 65
1.29 0.00 67
1.30 0.00 68
1.31 0.00 69
1.32 0.00 70
1.33 0.00 72
1.34 0.00 73
1.35 0.00 74
1.36 0.00 75
1.37 0.00 77
1.38 0.00 78
1.39 0.00 79
1.40 0.00 81
1.41 0.00 82
1.42 0.00 83
1.43 0.00 85
1.44 0.00 86
1.45 0.00 87
1.46 0.00 89
1.47 0.00 90
1.48 0.00 91
1.49 0.00 93
1.50 0.00 94
1.51 0.00 96
1.52 0.00 97
1.53 0.00 99
1.54 0.00 100
1.55 0.00 102
1.56 0.00 103
1.57 0.00 104
1.58 0.00 106
1.59 0.00 107
1.60 0.00 109
1.61 0.00 111
1.62 0.00 112
1.63 0.00 114
1.64 0.00 115
1.65 0.00 117
1.66 0.00 118
1.67 0.00 120
1.68 0.00 121
1.69 0.00 123
1.70 0.00 125
1.71 0.00 126
1.72 0.00 128
1.73 0.00 129
1.74 0.00 131
1.75 0.00 133
1.76 0.00 134
1.77 0.00 136
1.78 0.00 138
1.79 0.00 139
1.80 0.00 141
1.81 0.00 143
1.82 0.00 145
1.83 0.00 146
1.84 0.00 148
1.85 0.00 150
1.86 0.00 152
1.87 0.00 153
1.88 0.00 155
1.89 0.00 157
1.90 0.00 159
1.91 0.00 160
1.92 0.00 162
1.93 0.00 164
1.94 0.00 166
1.95 0.00 168
1.96 0.00 170
1.97 0.00 171
1.98 0.00 173
1.99 0.00 175
2.00 0.00 177
2.01 0.00 179
2.02 0.00 181
2.03 0.00 183
2.04 0.00 185
2.05 0.00 187
2.06 0.00 188
2.07 0.00 190
2.08 0.00 192
2.09 0.00 194
2.10 0.00 196
2.11 0.00 198
2.12 0.00 200
2.13 0.00 202
2.14 0.00 204
2.15 0.00 206
2.16 0.00 208
2.17 0.00 210
2.18 0.00 212
2.19 0.00 214
2.20 0.00 216
2.21 0.00 218
2.22 0.00 221
2.23 0.00 223
2.24 0.00 225
2.25 0.00 227
2.26 0.00 229
2.27 0.00 231
2.28 0.00 233
2.29 0.00 235
2.30 0.00 237
2.31 0.00 240
2.32 0.00 242
2.33 0.00 244
2.34 0.00 246
2.35 0.00 248
2.36 0.00 250
2.37 0.00 253
2.38 0.00 255
2.39 0.00 257
2.40 0.00 259
2.41 0.00 262
2.42 0.00 264
2.43 0.00 266
2.44 0.00 268
2.45 0.00 271
2.46 0.00 273
2.47 0.00 275
2.48 0.00 277
2.49 0.00 280
2.50 0.00 282
2.51 0.00 284
2.52 0.00 287
2.53 0.00 289
2.54 0.00 291
2.55 0.00 294
2.56 0.00 296
2.57 0.00 298
2.58 0.00 301
2.59 0.00 303
2.60 0.00 306
2.61 0.00 308
2.62 0.00 310
2.63 0.00 313
2.64 0.00 315
2.65 0.00 318
2.66 0.00 320
2.67 0.00 323
2.68 0.00 325
2.69 0.00 328
2.70 0.00 330
2.71 0.00 333
2.72 0.00 335
2.73 0.00 338
2.74 0.00 340
2.75 0.00 343
2.76 0.00 345
2.77 0.00 348
2.78 0.00 350
2.79 0.00 353
2.80 0.00 355
2.81 0.00 358
2.82 0.00 361
2.83 0.00 363
2.84 0.00 366
2.85 0.00 368
2.86 0.00 371
2.87 0.00 374
2.88 0.00 376
2.89 0.00 379
2.90 0.00 381
2.91 0.00 384
2.92 0.00 387
2.93 0.00 389
2.94 0.00 392
2.95 0.00 395
2.96 0.00 398
2.97 0.00 400
2.98 0.00 403
2.99 0.00 406
3.00 0.00 408
3.01 0.00 411
3.02 0.00 414
3.03 0.00 417
3.04 0.00 419
3.05 0.00 422
3.06 0.00 425
3.07 0.00 428
3.08 0.00 431
3.09 0.00 433
3.10 0.00 436
3.11 0.00 439
3.12 0.00 442
3.13 0.00 445
3.14 0.00 447
3.15 0.00 450
3.16 0.00 453
3.17 0.00 456
3.18 0.00 459
3.19 0.00 462
3.20 0.00 465
3.21 0.00 468
3.22 0.00 470
3.23 0.00 473
3.24 0.00 476
3.25 0.00 479
3.26 0.00 482
3.27 0.00 485
3.28 0.00 488
3.29 0.00 491
3.30 0.00 494
3.31 0.00 497
3.32 0.00 500
3.33 0.00 503
3.34 0.00 506
3.35 0.00 509
3.36 0.00 512
3.37 0.00 515
3.38 0.00 518
3.39 0.00 521
3.40 0.00 524
3.41 0.00 527
3.42 0.00 530
3.43 0.00 533
3.44 0.00 536
3.45 0.00 540
3.46 0.00 543
3.47 0.00 546
3.48 0.00 549
3.49 0.00 552
3.50 0.00 555
3.51 0.00 558
3.52 0.00 561
3.53 0.00 565
3.54 0.00 568
3.55 0.00 571
3.56 0.00 574
3.57 0.00 577
3.58 0.00 580
3.59 0.00 584
3.60 0.00 587
3.61 0.00 590
3.62 0.00 593
3.63 0.00 597
3.64 0.00 600
3.65 0.00 603
3.66 0.00 606
3.67 0.00 610
3.68 0.00 613
3.69 0.00 616
3.70 0.00 619
3.71 0.00 623
3.72 0.00 626
3.73 0.00 629
3.74 0.00 633
3.75 0.00 636
3.76 0.00 639
3.77 0.00 643
3.78 0.00 646
3.79 0.00 649
3.80 0.00 653
3.81 0.00 656
3.82 0.00 660
3.83 0.00 663
3.84 0.00 666
3.85 0.00 670
3.86 0.00 673
3.87 0.00 677
3.88 0.00 680
3.89 0.00 683
3.90 0.00 687
3.91 0.00 690
3.92 0.00 694
3.93 0.00 697
3.94 0.00 701
3.95 0.00 704
3.96 0.00 708
3.97 0.00 711
3.98 0.00 715
3.99 0.00 718
4.00 0.00 722
4.01 0.00 725
4.02 0.00 729
4.03 0.00 732
4.04 0.00 736
4.05 0.00 739
4.06 0.00 743
4.07 0.00 747
4.08 0.00 750
4.09 0.00 754
4.10 0.00 757
4.11 0.00 761
4.12 0.00 765
4.13 0.00 768
4.14 0.00 772
4.15 0.00 775
4.16 0.00 779
4.17 0.00 783
4.18 0.00 786
4.19 0.00 790
4.20 0.00 794
4.21 0.00 797
4.22 0.00 801
4.23 0.00 805
4.24 0.00 809
4.25 0.00 812
4.26 0.00 816
4.27 0.00 820
4.28 0.00 823
4.29 0.00 827
4.30 0.00 831
4.31 0.00 835
4.32 0.00 838
4.33 0.00 842
4.34 0.00 846
4.35 0.00 850
4.36 0.00 854
4.37 0.00 857
4.38 0.00 861
4.39 0.00 865
4.40 0.00 869
4.41 0.00 873
4.42 0.00 877
4.43 0.00 880
4.44 0.00 884
4.45 0.00 888
4.46 0.00 892
4.47 0.00 896
4.48 0.00 900
4.49 0.00 904
4.50 0.00 908
4.51 0.00 911
4.52 0.00 915
4.53 0.00 919
4.54 0.00 923
4.55 0.00 927
4.56 0.00 931
4.57 0.00 935
4.58 0.00 939
4.59 0.00 943
4.60 0.00 947
4.61 0.00 951
4.62 0.00 955
4.63 0.00 959
4.64 0.00 963
4.65 0.00 967
4.66 0.00 971
4.67 0.00 975
4.68 0.00 979
4.69 0.00 983
4.70 0.00 987
4.71 0.00 991
4.72 0.00 995
4.73 0.00 999
4.74 0.00 1000
4.75 0.00 1010
4.76 0.00 1010
4.77 0.00 1020
4.78 0.00 1020
4.79 0.00 1020
4.80 0.00 1030
4.81 0.00 1030
4.82 0.00 1040
4.83 0.00 1040
4.84 0.00 1040
4.85 0.00 1050
4.86 0.00 1050
4.87 0.00 1060
4.88 0.00 1060
4.89 0.00 1070
4.90 0.00 1070
4.91 0.00 1070
4.92 0.00 1080
4.93 0.00 1080
4.94 0.00 1090
4.95 0.00 1090
4.96 0.00 1100
4.97 0.00 1100
4.98 0.00 1100
4.99 0.00 1110
5.00 0.00 1110
5.01 0.00 1120
5.02 0.00 1120
5.03 0.00 1120
5.04 0.00 1130
5.05 0.00 1130
5.06 0.00 1140
5.07 0.00 1140
5.08 0.00 1150
5.09 0.00 1150
5.10 0.00 1160
5.11 0.00 1160
5.12 0.00 1160
5.13 0.00 1170
5.14 0.00 1170
5.15 0.00 1180
5.16 0.00 1180
5.17 0.00 1190
5.18 0.00 1190
5.19 0.00 1190
5.20 0.00 1200
5.21 0.00 1200
5.22 0.00 1210
5.23 0.00 1210
5.24 0.00 1220
5.25 0.00 1220
5.26 0.00 1230
5.27 0.00 1230
5.28 0.00 1230
5.29 0.00 1240
5.30 0.00 1240
5.31 0.00 1250
5.32 0.00 1250
5.33 0.00 1260
5.34 0.00 1260
5.35 0.00 1270
5.36 0.00 1270
5.37 0.00 1280
5.38 0.00 1280
5.39 0.00 1280
5.40 0.00 1290
5.41 0.00 1290
5.42 0.00 1300
5.43 0.00 1300
5.44 0.00 1310
5.45 0.00 1310
5.46 0.00 1320
5.47 0.00 1320
5.48 0.00 1330
5.49 0.00 1330
5.50 0.00 1340
5.51 0.00 1340
5.52 0.00 1340
5.53 0.00 1350
5.54 0.00 1350
5.55 0.00 1360
5.56 0.00 1360
5.57 0.00 1370
5.58 0.00 1370
5.59 0.00 1380
5.60 0.00 1380
5.61 0.00 1390
5.62 0.00 1390
5.63 0.00 1400
5.64 0.00 1400
5.65 0.00 1410
5.66 0.00 1410
5.67 0.00 1410
5.68 0.00 1420
5.69 0.00 1420
5.70 0.00 1430
5.71 0.00 1430
5.72 0.00 1440
5.73 0.00 1440
5.74 0.00 1450
5.75 0.00 1450
5.76 0.00 1460
5.77 0.00 1460
5.78 0.00 1470
5.79 0.00 1470
5.80 0.00 1480
5.81 0.00 1480
5.82 0.00 1490
5.83 0.00 1490
5.84 0.00 1500
5.85 0.00 1500
5.86 0.00 1510
5.87 0.00 1510
5.88 0.00 1520
5.89 0.00 1520
5.90 0.00 1530
5.91 0.00 1530
5.92 0.00 1540
5.93 0.00 1540
5.94 0.00 1550
5.95 0.00 1550
5.96 0.00 1560
5.97 0.00 1560
5.98 0.00 1570
5.99 0.00 1570
6.00 0.00 1580 *
6.01 0.00 1580
6.02 0.00 1590
6.03 0.00 1590
6.04 0.00 1600
6.05 0.00 1600
6.06 0.00 1610
6.07 0.00 1610
6.08 0.00 1620
6.09 0.00 1620
6.10 0.00 1630
6.11 0.00 1630
6.12 0.00 1640
6.13 0.00 1640
6.14 0.00 1650
6.15 0.00 1650
6.16 0.00 1660
6.17 0.00 1660
6.18 0.00 1670
6.19 0.00 1670
6.20 0.00 1680
6.21 0.00 1680
6.22 0.00 1690
6.23 0.00 1690
6.24 0.00 1700
6.25 0.00 1700
6.26 0.00 1710
6.27 0.00 1710
6.28 0.00 1720
6.29 0.00 1720
6.30 0.00 1730
6.31 0.00 1730
6.32 0.00 1740
6.33 0.00 1740
6.34 0.00 1750
6.35 0.00 1750
6.36 0.00 1760
6.37 0.00 1760
6.38 0.00 1770
6.39 0.00 1770
6.40 0.00 1780
6.41 0.00 1780
6.42 0.00 1790
6.43 0.00 1790
6.44 0.00 1800
6.45 0.00 1800
6.46 0.00 1810
6.47 0.00 1810
6.48 0.00 1820
6.49 0.00 1830
6.50 0.00 1830
6.51 0.00 1840
6.52 0.00 1840
6.53 0.00 1850
6.54 0.00 1850
6.55 0.00 1860
6.56 0.00 1860
6.57 0.00 1870
6.58 0.00 1870
6.59 0.00 1880
6.60 0.00 1880
6.61 0.00 1890
6.62 0.00 1890
6.63 0.00 1900
6.64 0.00 1910
6.65 0.00 1910
6.66 0.00 1920
6.67 0.00 1920
6.68 0.00 1930
6.69 0.00 1930
6.70 0.00 1940
6.71 0.00 1940
6.72 0.00 1950
6.73 0.00 1950
6.74 0.00 1960
6.75 0.00 1960
6.76 0.00 1970
6.77 0.00 1980
6.78 0.00 1980
6.79 0.00 1990
6.80 0.00 1990
6.81 0.00 2000
6.82 0.00 2000
6.83 0.00 2010
6.84 0.00 2010
6.85 0.00 2020
6.86 0.00 2020
6.87 0.00 2030
6.88 0.00 2040
6.89 0.00 2040
6.90 0.00 2050
6.91 0.00 2050
6.92 0.00 2060
6.93 0.00 2060
6.94 0.00 2070
6.95 0.00 2070
6.96 0.00 2080
6.97 0.00 2090
6.98 0.00 2090
6.99 0.00 2100
7.00 0.00 2100 *
7.01 0.00 2110
7.02 0.00 2110
7.03 0.00 2120
7.04 0.00 2120
7.05 0.00 2130
7.06 0.00 2130
7.07 0.00 2140
7.08 0.00 2140
7.09 0.00 2150
7.10 0.00 2160
7.11 0.00 2160
7.12 0.00 2170
7.13 0.00 2170
7.14 0.00 2180
7.15 0.00 2180
7.16 0.00 2190
7.17 0.00 2190
7.18 0.00 2200
7.19 0.00 2200
7.20 0.00 2210
7.21 0.00 2210
7.22 0.00 2220
7.23 0.00 2220
7.24 0.00 2230
7.25 0.00 2240
7.26 0.00 2240
7.27 0.00 2250
7.28 0.00 2250
7.29 0.00 2260
7.30 0.00 2260
7.31 0.00 2270
7.32 0.00 2270
7.33 0.00 2280
7.34 0.00 2280
7.35 0.00 2290
7.36 0.00 2300
7.37 0.00 2300
7.38 0.00 2310
7.39 0.00 2310
7.40 0.00 2320
7.41 0.00 2320
7.42 0.00 2330
7.43 0.00 2330
7.44 0.00 2340
7.45 0.00 2340
7.46 0.00 2350
7.47 0.00 2360
7.48 0.00 2360
7.49 0.00 2370
7.50 0.00 2370
7.51 0.00 2380
7.52 0.00 2380
7.53 0.00 2390
7.54 0.00 2390
7.55 0.00 2400
7.56 0.00 2410
7.57 0.00 2410
7.58 0.00 2420
7.59 0.00 2420
7.60 0.00 2430
7.61 0.00 2430
7.62 0.00 2440
7.63 0.00 2440
7.64 0.00 2450
7.65 0.00 2460
7.66 0.00 2460
7.67 0.00 2470
7.68 0.00 2470
7.69 0.00 2480
7.70 0.00 2480
7.71 0.00 2490
7.72 0.00 2500
7.73 0.00 2500
7.74 0.00 2510
7.75 0.00 2510
7.76 0.00 2520
7.77 0.00 2520
7.78 0.00 2530
7.79 0.00 2540
7.80 0.00 2540
7.81 0.00 2550
7.82 0.00 2550
7.83 0.00 2560
7.84 0.00 2560
7.85 0.00 2570
7.86 0.00 2580
7.87 0.00 2580
7.88 0.00 2590
7.89 0.00 2590
7.90 0.00 2600
7.91 0.00 2600
7.92 0.00 2610
7.93 0.00 2620
7.94 0.00 2620
7.95 0.00 2630
7.96 0.00 2630
7.97 0.00 2640
7.98 0.00 2640
7.99 0.00 2650
8.00 0.00 2660
8.01 0.00 2660
8.02 0.00 2670
8.03 0.00 2670
8.04 0.00 2680
8.05 0.00 2680
8.06 0.00 2690
8.07 0.00 2700
8.08 0.00 2700
8.09 0.00 2710
8.10 0.00 2710
8.11 0.00 2720
8.12 0.00 2730
8.13 0.00 2730
8.14 0.00 2740
8.15 0.00 2740
8.16 0.00 2750
8.17 0.00 2760
8.18 0.00 2760
8.19 0.00 2770
8.20 0.00 2770
8.21 0.00 2780
8.22 0.00 2780
8.23 0.00 2790
8.24 0.00 2800
8.25 0.00 2800
8.26 0.00 2810
8.27 0.00 2810
8.28 0.00 2820
8.29 0.00 2830
8.30 0.00 2830
8.31 0.00 2840
8.32 0.00 2840
8.33 0.00 2850
8.34 0.00 2860
8.35 0.00 2860
8.36 0.00 2870
8.37 0.00 2870
8.38 0.00 2880
8.39 0.00 2890
8.40 0.00 2890
8.41 0.00 2900
8.42 0.00 2900
8.43 0.00 2910
8.44 0.00 2920
8.45 0.00 2920
8.46 0.00 2930
8.47 0.00 2930
8.48 0.00 2940
8.49 0.00 2950
8.50 0.00 2950
8.51 0.00 2960
8.52 0.00 2960
8.53 0.00 2970
8.54 0.00 2980
8.55 0.00 2980
8.56 0.00 2990
8.57 0.00 2990
8.58 0.00 3000
8.59 0.00 3010
8.60 0.00 3010
8.61 0.00 3020
8.62 0.00 3030
8.63 0.00 3030
8.64 0.00 3040
8.65 0.00 3040
8.66 0.00 3050
8.67 0.00 3060
8.68 0.00 3060
8.69 0.00 3070
8.70 0.00 3070
8.71 0.00 3080
8.72 0.00 3090
8.73 0.00 3090
8.74 0.00 3100
8.75 0.00 3110
8.76 0.00 3110
8.77 0.00 3120
8.78 0.00 3120
8.79 0.00 3130
8.80 0.00 3140
8.81 0.00 3140
8.82 0.00 3150
8.83 0.00 3150
8.84 0.00 3160
8.85 0.00 3170
8.86 0.00 3170
8.87 0.00 3180
8.88 0.00 3190
8.89 0.00 3190
8.90 0.00 3200
8.91 0.00 3200
8.92 0.00 3210
8.93 0.00 3220
8.94 0.00 3220
8.95 0.00 3230
8.96 0.00 3240
8.97 0.00 3240
8.98 0.00 3250
8.99 0.00 3250
9.00 0.00 3260
9.01 0.00 3270
9.02 0.00 3270
9.03 0.00 3280
9.04 0.00 3290
9.05 0.00 3290
9.06 0.00 3300
9.07 0.00 3310
9.08 0.00 3310
9.09 0.00 3320
9.10 0.00 3320
9.11 0.00 3330
9.12 0.00 3340
9.13 0.00 3340
9.14 0.00 3350
9.15 0.00 3360
9.16 0.00 3360
9.17 0.00 3370
9.18 0.00 3380
9.19 0.00 3380
9.20 0.00 3390
9.21 0.00 3390
9.22 0.00 3400
9.23 0.00 3410
9.24 0.00 3410
9.25 0.00 3420
9.26 0.00 3430
9.27 0.00 3430
9.28 0.00 3440
9.29 0.00 3450
9.30 0.00 3450
9.31 0.00 3460
9.32 0.00 3470
9.33 0.00 3470
9.34 0.00 3480
9.35 0.00 3480
9.36 0.00 3490
9.37 0.00 3500
9.38 0.00 3500
9.39 0.00 3510
9.40 0.00 3520
9.41 0.00 3520
9.42 0.00 3530
9.43 0.00 3540
9.44 0.00 3540
9.45 0.00 3550
9.46 0.00 3560
9.47 0.00 3560
9.48 0.00 3570
9.49 0.00 3580
9.50 0.00 3580
9.51 0.00 3590
9.52 0.00 3600
9.53 0.00 3600
9.54 0.00 3610
9.55 0.00 3620
9.56 0.00 3620
9.57 0.00 3630
9.58 0.00 3630
9.59 0.00 3640
9.60 0.00 3650
9.61 0.00 3650
9.62 0.00 3660
9.63 0.00 3670
9.64 0.00 3670
9.65 0.00 3680
9.66 0.00 3690
9.67 0.00 3690
9.68 0.00 3700
9.69 0.00 3710
9.70 0.00 3710
9.71 0.00 3720
9.72 0.00 3730
9.73 0.00 3730
9.74 0.00 3740
9.75 0.00 3750
9.76 0.00 3750
9.77 0.00 3760
9.78 0.00 3770
9.79 0.00 3770
9.80 0.00 3780
9.81 0.00 3790
9.82 0.00 3790
9.83 0.00 3800
9.84 0.00 3810
9.85 0.00 3810
9.86 0.00 3820
9.87 0.00 3830
9.88 0.00 3830
9.89 0.00 3840
9.90 0.00 3850
9.91 0.00 3850
9.92 0.00 3860
9.93 0.00 3870
9.94 0.00 3880
9.95 0.00 3880
9.96 0.00 3890
9.97 0.00 3900
9.98 0.00 3900
9.99 0.00 3910
10.00 0.00 3920
10.01 0.00 3920
10.02 0.00 3930
10.03 0.00 3940
10.04 0.00 3940
10.05 0.00 3950
10.06 0.00 3960
10.07 0.00 3960
10.08 0.00 3970
10.09 0.00 3980
10.10 0.00 3980
10.11 0.00 3990
10.12 0.00 4000
10.13 0.00 4000
10.14 0.00 4010
10.15 0.00 4020
10.16 0.00 4020
10.17 0.00 4030
10.18 0.00 4040
10.19 0.00 4050
10.20 0.00 4050
10.21 0.00 4060
10.22 0.00 4070
10.23 0.00 4070
10.24 0.00 4080
10.25 0.00 4090
10.26 0.00 4090
10.27 0.00 4100
10.28 0.00 4110
10.29 0.00 4110
10.30 0.00 4120
10.31 0.00 4130
10.32 0.00 4140
10.33 0.00 4140
10.34 0.00 4150
10.35 0.00 4160
10.36 0.00 4160
10.37 0.00 4170
10.38 0.00 4180
10.39 0.00 4180
10.40 0.00 4190
10.41 0.00 4200
10.42 0.00 4200
10.43 0.00 4210
10.44 0.00 4220
10.45 0.00 4230
10.46 0.00 4230
10.47 0.00 4240
10.48 0.00 4250
10.49 0.00 4250
10.50 0.00 4260
10.51 0.00 4270
10.52 0.00 4280
10.53 0.00 4280
10.54 0.00 4290
10.55 0.00 4300
10.56 0.00 4300
10.57 0.00 4310
10.58 0.00 4320
10.59 0.00 4320
10.60 0.00 4330
10.61 0.00 4340
10.62 0.00 4350
10.63 0.00 4350
10.64 0.00 4360
10.65 0.00 4370
10.66 0.00 4370
10.67 0.00 4380
10.68 0.00 4390
10.69 0.00 4400
10.70 0.00 4400
10.71 0.00 4410
10.72 0.00 4420
10.73 0.00 4420
10.74 0.00 4430
10.75 0.00 4440
10.76 0.00 4450
10.77 0.00 4450
10.78 0.00 4460
10.79 0.00 4470
10.80 0.00 4470
10.81 0.00 4480
10.82 0.00 4490
10.83 0.00 4500
10.84 0.00 4500
10.85 0.00 4510
10.86 0.00 4520
10.87 0.00 4520
10.88 0.00 4530
10.89 0.00 4540
10.90 0.00 4550
10.91 0.00 4550
10.92 0.00 4560
10.93 0.00 4570
10.94 0.00 4570
10.95 0.00 4580
10.96 0.00 4590
10.97 0.00 4600
10.98 0.00 4600
10.99 0.00 4610
11.00 0.00 4620
11.01 0.00 4630
11.02 0.00 4630
11.03 0.00 4640
11.04 0.00 4650
11.05 0.00 4650
11.06 0.00 4660
11.07 0.00 4670
11.08 0.00 4680
11.09 0.00 4680
11.10 0.00 4690
11.11 0.00 4700
11.12 0.00 4710
11.13 0.00 4710
11.14 0.00 4720
11.15 0.00 4730
11.16 0.00 4730
11.17 0.00 4740
11.18 0.00 4750
11.19 0.00 4760
11.20 0.00 4760
11.21 0.00 4770
11.22 0.00 4780
11.23 0.00 4790
11.24 0.00 4790
11.25 0.00 4800
11.26 0.00 4810
11.27 0.00 4820
11.28 0.00 4820
11.29 0.00 4830
11.30 0.00 4840
11.31 0.00 4850
11.32 0.00 4850
11.33 0.00 4860
11.34 0.00 4870
11.35 0.00 4870
11.36 0.00 4880
11.37 0.00 4890
11.38 0.00 4900
11.39 0.00 4900
11.40 0.00 4910
11.41 0.00 4920
11.42 0.00 4930
11.43 0.00 4930
11.44 0.00 4940
11.45 0.00 4950
11.46 0.00 4960
11.47 0.00 4960
11.48 0.00 4970
11.49 0.00 4980
11.50 0.00 4990
11.51 0.00 4990
11.52 0.00 5000
11.53 0.00 5010
11.54 0.00 5020
11.55 0.00 5020
11.56 0.00 5030
11.57 0.00 5040
11.58 0.00 5050
11.59 0.00 5050
11.60 0.00 5060
11.61 0.00 5070
11.62 0.00 5080
11.63 0.00 5080
11.64 0.00 5090
11.65 0.00 5100
11.66 0.00 5110
11.67 0.00 5110
11.68 0.00 5120
11.69 0.00 5130
11.70 0.00 5140
11.71 0.00 5140
11.72 0.00 5150
11.73 0.00 5160
11.74 0.00 5170
11.75 0.00 5180
11.76 0.00 5180
11.77 0.00 5190
11.78 0.00 5200
11.79 0.00 5210
11.80 0.00 5210
11.81 0.00 5220
11.82 0.00 5230
11.83 0.00 5240
11.84 0.00 5240
11.85 0.00 5250
11.86 0.00 5260
11.87 0.00 5270
11.88 0.00 5270
11.89 0.00 5280
11.90 0.00 5290
11.91 0.00 5300
11.92 0.00 5300
11.93 0.00 5310
11.94 0.00 5320
11.95 0.00 5330
11.96 0.00 5340
11.97 0.00 5340
11.98 0.00 5350
11.99 0.00 5360
12.00 0.00 5370
12.01 0.00 5370
12.02 0.00 5380
12.03 0.00 5390
12.04 0.00 5400
12.05 0.00 5410
12.06 0.00 5410
12.07 0.00 5420
12.08 0.00 5430
12.09 0.00 5440
12.10 0.00 5440
12.11 0.00 5450
12.12 0.00 5460
12.13 0.00 5470
12.14 0.00 5470
12.15 0.00 5480
12.16 0.00 5490
12.17 0.00 5500
12.18 0.00 5510
12.19 0.00 5510
12.20 0.00 5520
12.21 0.00 5530
12.22 0.00 5540
12.23 0.00 5550
12.24 0.00 5550
12.25 0.00 5560
12.26 0.00 5570
12.27 0.00 5580
12.28 0.00 5580
12.29 0.00 5590
12.30 0.00 5600
12.31 0.00 5610
12.32 0.00 5620
12.33 0.00 5620
12.34 0.00 5630
12.35 0.00 5640
12.36 0.00 5650
12.37 0.00 5650
12.38 0.00 5660
12.39 0.00 5670
12.40 0.00 5680
12.41 0.00 5690
12.42 0.00 5690
12.43 0.00 5700
12.44 0.00 5710
12.45 0.00 5720
12.46 0.00 5730
12.47 0.00 5730
12.48 0.00 5740
12.49 0.00 5750
12.50 0.00 5760
12.51 0.00 5770
12.52 0.00 5770
12.53 0.00 5780
12.54 0.00 5790
12.55 0.00 5800
12.56 0.00 5810
12.57 0.00 5810
12.58 0.00 5820
12.59 0.00 5830
12.60 0.00 5840
12.61 0.00 5850
12.62 0.00 5850
12.63 0.00 5860
12.64 0.00 5870
12.65 0.00 5880
12.66 0.00 5890
12.67 0.00 5890
12.68 0.00 5900
12.69 0.00 5910
12.70 0.00 5920
12.71 0.00 5930
12.72 0.00 5930
12.73 0.00 5940
12.74 0.00 5950
12.75 0.00 5960
12.76 0.00 5970
12.77 0.00 5970
12.78 0.00 5980
12.79 0.00 5990
12.80 0.00 6000
12.81 0.00 6010
12.82 0.00 6010
12.83 0.00 6020
12.84 0.00 6030
12.85 0.00 6040
12.86 0.00 6050
12.87 0.00 6050
12.88 0.00 6060
12.89 0.00 6070
12.90 0.00 6080
12.91 0.00 6090
12.92 0.00 6090
12.93 0.00 6100
12.94 0.00 6110
12.95 0.00 6120
12.96 0.00 6130
12.97 0.00 6140
12.98 0.00 6140
12.99 0.00 6150
13.00 0.00 6160
13.01 0.00 6170
13.02 0.00 6180
13.03 0.00 6180
13.04 0.00 6190
13.05 0.00 6200
13.06 0.00 6210
13.07 0.00 6220
13.08 0.00 6230
13.09 0.00 6230
13.10 0.00 6240
13.11 0.00 6250
13.12 0.00 6260
13.13 0.00 6270
13.14 0.00 6270
13.15 0.00 6280
13.16 0.00 6290
13.17 0.00 6300
13.18 0.00 6310
13.19 0.00 6320
13.20 0.00 6320
13.21 0.00 6330
13.22 0.00 6340
13.23 0.00 6350
13.24 0.00 6360
13.25 0.00 6370
13.26 0.00 6370
13.27 0.00 6380
13.28 0.00 6390
13.29 0.00 6400
13.30 0.00 6410
13.31 0.00 6410
13.32 0.00 6420
13.33 0.00 6430
13.34 0.00 6440
13.35 0.00 6450
13.36 0.00 6460
13.37 0.00 6460
13.38 0.00 6470
13.39 0.00 6480
13.40 0.00 6490
13.41 0.00 6500
13.42 0.00 6510
13.43 0.00 6510
13.44 0.00 6520
13.45 0.00 6530
13.46 0.00 6540
13.47 0.00 6550
13.48 0.00 6560
13.49 0.00 6560
13.50 0.00 6570
13.51 0.00 6580
13.52 0.00 6590
13.53 0.00 6600
13.54 0.00 6610
13.55 0.00 6620
13.56 0.00 6620
13.57 0.00 6630
13.58 0.00 6640
13.59 0.00 6650
13.60 0.00 6660
13.61 0.00 6670
13.62 0.00 6670
13.63 0.00 6680
13.64 0.00 6690
13.65 0.00 6700
13.66 0.00 6710
13.67 0.00 6720
13.68 0.00 6720
13.69 0.00 6730
13.70 0.00 6740
13.71 0.00 6750
13.72 0.00 6760
13.73 0.00 6770
13.74 0.00 6780
13.75 0.00 6780
13.76 0.00 6790
13.77 0.00 6800
13.78 0.00 6810
13.79 0.00 6820
13.80 0.00 6830
13.81 0.00 6830
13.82 0.00 6840
13.83 0.00 6850
13.84 0.00 6860
13.85 0.00 6870
13.86 0.00 6880
13.87 0.00 6890
13.88 0.00 6890
13.89 0.00 6900
13.90 0.00 6910
13.91 0.00 6920
13.92 0.00 6930
13.93 0.00 6940
13.94 0.00 6950
13.95 0.00 6950
13.96 0.00 6960
13.97 0.00 6970
13.98 0.00 6980
13.99 0.00 6990
14.00 0.00 7000
14.01 0.00 7010
14.02 0.00 7010
14.03 0.00 7020
14.04 0.00 7030
14.05 0.00 7040
14.06 0.00 7050
14.07 0.00 7060
14.08 0.00 7070
14.09 0.00 7070
14.10 0.00 7080
14.11 0.00 7090
14.12 0.00 7100
14.13 0.00 7110
14.14 0.00 7120
14.15 0.00 7130
14.16 0.00 7140
14.17 0.00 7140
14.18 0.00 7150
14.19 0.00 7160
14.20 0.00 7170
14.21 0.00 7180
14.22 0.00 7190
14.23 0.00 7200
14.24 0.00 7200
14.25 0.00 7210
14.26 0.00 7220
14.27 0.00 7230
14.28 0.00 7240
14.29 0.00 7250
14.30 0.00 7260
14.31 0.00 7270
14.32 0.00 7270
14.33 0.00 7280
14.34 0.00 7290
14.35 0.00 7300
14.36 0.00 7310
14.37 0.00 7320
14.38 0.00 7330
14.39 0.00 7340
14.40 0.00 7340
14.41 0.00 7350
14.42 0.00 7360
14.43 0.00 7370
14.44 0.00 7380
14.45 0.00 7390
14.46 0.00 7400
14.47 0.00 7410
14.48 0.00 7410
14.49 0.00 7420
14.50 0.00 7430
14.51 0.00 7440
14.52 0.00 7450
14.53 0.00 7460
14.54 0.00 7470
14.55 0.00 7480
14.56 0.00 7480
14.57 0.00 7490
14.58 0.00 7500
14.59 0.00 7510
14.60 0.00 7520
14.61 0.00 7530
14.62 0.00 7540
14.63 0.00 7550
14.64 0.00 7560
14.65 0.00 7560
14.66 0.00 7570
14.67 0.00 7580
14.68 0.00 7590
14.69 0.00 7600
14.70 0.00 7610
14.71 0.00 7620
14.72 0.00 7630
14.73 0.00 7640
14.74 0.00 7640
14.75 0.00 7650
14.76 0.00 7660
14.77 0.00 7670
14.78 0.00 7680
14.79 0.00 7690
14.80 0.00 7700
14.81 0.00 7710
14.82 0.00 7720
14.83 0.00 7720
14.84 0.00 7730
14.85 0.00 7740
14.86 0.00 7750
14.87 0.00 7760
14.88 0.00 7770
14.89 0.00 7780
14.90 0.00 7790
14.91 0.00 7800
14.92 0.00 7810
14.93 0.00 7810
14.94 0.00 7820
14.95 0.00 7830
14.96 0.00 7840
14.97 0.00 7850
14.98 0.00 7860
14.99 0.00 7870
15.00 0.00 7880
15.01 0.00 7890
15.02 0.00 7900
15.03 0.00 7900
15.04 0.00 7910
15.05 0.00 7920
15.06 0.00 7930
15.07 0.00 7940
15.08 0.00 7950
15.09 0.00 7960
15.10 0.00 7970
15.11 0.00 7980
15.12 0.00 7990
15.13 0.00 7990
15.14 0.00 8000
15.15 0.00 8010
15.16 0.00 8020
15.17 0.00 8030
15.18 0.00 8040
15.19 0.00 8050
15.20 0.00 8060
15.21 0.00 8070
15.22 0.00 8080
15.23 0.00 8090
15.24 0.00 8090
15.25 0.00 8100
15.26 0.00 8110
15.27 0.00 8120
15.28 0.00 8130
15.29 0.00 8140
15.30 0.00 8150
15.31 0.00 8160
15.32 0.00 8170
15.33 0.00 8180
15.34 0.00 8190
15.35 0.00 8190
15.36 0.00 8200
15.37 0.00 8210
15.38 0.00 8220
15.39 0.00 8230
15.40 0.00 8240
15.41 0.00 8250
15.42 0.00 8260
15.43 0.00 8270
15.44 0.00 8280
15.45 0.00 8290
15.46 0.00 8300
15.47 0.00 8310
15.48 0.00 8310
15.49 0.00 8320
15.50 0.00 8330
15.51 0.00 8340
15.52 0.00 8350
15.53 0.00 8360
15.54 0.00 8370
15.55 0.00 8380
15.56 0.00 8390
15.57 0.00 8400
15.58 0.00 8410
15.59 0.00 8420
15.60 0.00 8430
15.61 0.00 8430
15.62 0.00 8440
15.63 0.00 8450
15.64 0.00 8460
15.65 0.00 8470
15.66 0.00 8480
15.67 0.00 8490
15.68 0.00 8500
15.69 0.00 8510
15.70 0.00 8520
15.71 0.00 8530
15.72 0.00 8540
15.73 0.00 8550
15.74 0.00 8560
15.75 0.00 8560
15.76 0.00 8570
15.77 0.00 8580
15.78 0.00 8590
15.79 0.00 8600
15.80 0.00 8610
15.81 0.00 8620
15.82 0.00 8630
15.83 0.00 8640
15.84 0.00 8650
15.85 0.00 8660
15.86 0.00 8670
15.87 0.00 8680
15.88 0.00 8690
15.89 0.00 8700
15.90 0.00 8700
15.91 0.00 8710
15.92 0.00 8720
15.93 0.00 8730
15.94 0.00 8740
15.95 0.00 8750
15.96 0.00 8760
15.97 0.00 8770
15.98 0.00 8780
15.99 0.00 8790
16.00 0.00 8800
16.01 0.00 8810
16.02 0.00 8820
16.03 0.00 8830
16.04 0.00 8840
16.05 0.00 8850
16.06 0.00 8860
16.07 0.00 8860
16.08 0.00 8870
16.09 0.00 8880
16.10 0.00 8890
16.11 0.00 8900
16.12 0.00 8910
16.13 0.00 8920
16.14 0.00 8930
16.15 0.00 8940
16.16 0.00 8950
16.17 0.00 8960
16.18 0.00 8970
16.19 0.00 8980
16.20 0.00 8990
16.21 0.00 9000
16.22 0.00 9010
16.23 0.00 9020
16.24 0.00 9030
16.25 0.00 9040
16.26 0.00 9040
16.27 0.00 9050
16.28 0.00 9060
16.29 0.00 9070
16.30 0.00 9080
16.31 0.00 9090
16.32 0.00 9100
16.33 0.00 9110
16.34 0.00 9120
16.35 0.00 9130
16.36 0.00 9140
16.37 0.00 9150
16.38 0.00 9160
16.39 0.00 9170
16.40 0.00 9180
16.41 0.00 9190
16.42 0.00 9200
16.43 0.00 9210
16.44 0.00 9220
16.45 0.00 9230
16.46 0.00 9240
16.47 0.00 9250
16.48 0.00 9260
16.49 0.00 9270
16.50 0.00 9270
16.51 0.00 9280
16.52 0.00 9290
16.53 0.00 9300
16.54 0.00 9310
16.55 0.00 9320
16.56 0.00 9330
16.57 0.00 9340
16.58 0.00 9350
16.59 0.00 9360
16.60 0.00 9370
16.61 0.00 9380
16.62 0.00 9390
16.63 0.00 9400
16.64 0.00 9410
16.65 0.00 9420
16.66 0.00 9430
16.67 0.00 9440
16.68 0.00 9450
16.69 0.00 9460
16.70 0.00 9470
16.71 0.00 9480
16.72 0.00 9490
16.73 0.00 9500
16.74 0.00 9510
16.75 0.00 9520
16.76 0.00 9530
16.77 0.00 9540
16.78 0.00 9550
16.79 0.00 9560
16.80 0.00 9570
16.81 0.00 9580
16.82 0.00 9580
16.83 0.00 9590
16.84 0.00 9600
16.85 0.00 9610
16.86 0.00 9620
16.87 0.00 9630
16.88 0.00 9640
16.89 0.00 9650
16.90 0.00 9660
16.91 0.00 9670
16.92 0.00 9680
16.93 0.00 9690
16.94 0.00 9700
16.95 0.00 9710
16.96 0.00 9720
16.97 0.00 9730
16.98 0.00 9740
16.99 0.00 9750
17.00 0.00 9760
17.01 0.00 9770
17.02 0.00 9780
17.03 0.00 9790
17.04 0.00 9800
17.05 0.00 9810
17.06 0.00 9820
17.07 0.00 9830
17.08 0.00 9840
17.09 0.00 9850
17.10 0.00 9860
17.11 0.00 9870
17.12 0.00 9880
17.13 0.00 9890
17.14 0.00 9900
17.15 0.00 9910
17.16 0.00 9920
17.17 0.00 9930
17.18 0.00 9940
17.19 0.00 9950
17.20 0.00 9960
17.21 0.00 9970
17.22 0.00 9980
17.23 0.00 9990
17.24 0.00 10000
17.25 0.00 10000
17.26 0.00 10000
17.27 0.00 10000
17.28 0.00 10000
17.29 0.00 10000
17.30 0.00 10100
17.31 0.00 10100
17.32 0.00 10100
17.33 0.00 10100
17.34 0.00 10100
17.35 0.00 10100
17.36 0.00 10100
17.37 0.00 10100
17.38 0.00 10100
17.39 0.00 10100
17.40 0.00 10200
17.41 0.00 10200
17.42 0.00 10200
17.43 0.00 10200
17.44 0.00 10200
17.45 0.00 10200
17.46 0.00 10200
17.47 0.00 10200
17.48 0.00 10200
17.49 0.00 10200
17.50 0.00 10300
17.51 0.00 10300
17.52 0.00 10300
17.53 0.00 10300
17.54 0.00 10300
17.55 0.00 10300
17.56 0.00 10300
17.57 0.00 10300
17.58 0.00 10300
17.59 0.00 10300
17.60 0.00 10400
17.61 0.00 10400
17.62 0.00 10400
17.63 0.00 10400
17.64 0.00 10400
17.65 0.00 10400
17.66 0.00 10400
17.67 0.00 10400
17.68 0.00 10400
17.69 0.00 10400
17.70 0.00 10500
17.71 0.00 10500
17.72 0.00 10500
17.73 0.00 10500
17.74 0.00 10500
17.75 0.00 10500
17.76 0.00 10500
17.77 0.00 10500
17.78 0.00 10500
17.79 0.00 10500
17.80 0.00 10600
17.81 0.00 10600
17.82 0.00 10600
17.83 0.00 10600
17.84 0.00 10600
17.85 0.00 10600
17.86 0.00 10600
17.87 0.00 10600
17.88 0.00 10600
17.89 0.00 10700
17.90 0.00 10700
17.91 0.00 10700
17.92 0.00 10700
17.93 0.00 10700
17.94 0.00 10700
17.95 0.00 10700
17.96 0.00 10700
17.97 0.00 10700
17.98 0.00 10700
17.99 0.00 10800
18.00 0.00 10800
18.01 0.00 10800
18.02 0.00 10800
18.03 0.00 10800
18.04 0.00 10800
18.05 0.00 10800
18.06 0.00 10800
18.07 0.00 10800
18.08 0.00 10800
18.09 0.00 10900
18.10 0.00 10900
18.11 0.00 10900
18.12 0.00 10900
18.13 0.00 10900
18.14 0.00 10900
18.15 0.00 10900
18.16 0.00 10900
18.17 0.00 10900
18.18 0.00 10900
18.19 0.00 11000
18.20 0.00 11000
18.21 0.00 11000
18.22 0.00 11000
18.23 0.00 11000 *
18.24 0.00 11000
18.25 0.00 11000
18.26 0.00 11000
18.27 0.00 11000
18.28 0.00 11100
18.29 0.00 11100
18.30 0.00 11100
18.31 0.00 11100
18.32 0.00 11100
18.33 0.00 11100
18.34 0.00 11100
18.35 0.00 11100
18.36 0.00 11200
18.37 0.00 11200
18.38 0.00 11200
18.39 0.00 11200
18.40 0.00 11200
18.41 0.00 11200
18.42 0.00 11200
18.43 0.00 11200
18.44 0.00 11300
18.45 0.00 11300
18.46 0.00 11300
18.47 0.00 11300
18.48 0.00 11300
18.49 0.00 11300
18.50 0.00 11300
18.51 0.00 11400
18.52 0.00 11400
18.53 0.00 11400
18.54 0.00 11400
18.55 0.00 11400
18.56 0.00 11400
18.57 0.00 11400
18.58 0.00 11400
18.59 0.00 11500
18.60 0.00 11500
18.61 0.00 11500
18.62 0.00 11500
18.63 0.00 11500
18.64 0.00 11500
18.65 0.00 11500
18.66 0.00 11500
18.67 0.00 11600
18.68 0.00 11600
18.69 0.00 11600
18.70 0.00 11600
18.71 0.00 11600
18.72 0.00 11600
18.73 0.00 11600
18.74 0.00 11600
18.75 0.00 11700
18.76 0.00 11700
18.77 0.00 11700
18.78 0.00 11700
18.79 0.00 11700
18.80 0.00 11700
18.81 0.00 11700
18.82 0.00 11700
18.83 0.00 11800
18.84 0.00 11800
18.85 0.00 11800
18.86 0.00 11800
18.87 0.00 11800
18.88 0.00 11800
18.89 0.00 11800
18.90 0.00 11800
18.91 0.00 11900
18.92 0.00 11900
18.93 0.00 11900
18.94 0.00 11900
18.95 0.00 11900
18.96 0.00 11900
18.97 0.00 11900
18.98 0.00 12000
18.99 0.00 12000
19.00 0.00 12000
19.01 0.00 12000
19.02 0.00 12000
19.03 0.00 12000
19.04 0.00 12000
19.05 0.00 12000
19.06 0.00 12100
19.07 0.00 12100
19.08 0.00 12100
19.09 0.00 12100
19.10 0.00 12100
19.11 0.00 12100
19.12 0.00 12100
19.13 0.00 12100
19.14 0.00 12200
19.15 0.00 12200
19.16 0.00 12200
19.17 0.00 12200
19.18 0.00 12200
19.19 0.00 12200
19.20 0.00 12200
19.21 0.00 12200
19.22 0.00 12300
19.23 0.00 12300
19.24 0.00 12300
19.25 0.00 12300
19.26 0.00 12300
19.27 0.00 12300
19.28 0.00 12300
19.29 0.00 12400
19.30 0.00 12400
19.31 0.00 12400
19.32 0.00 12400
19.33 0.00 12400
19.34 0.00 12400
19.35 0.00 12400
19.36 0.00 12400
19.37 0.00 12500
19.38 0.00 12500
19.39 0.00 12500
19.40 0.00 12500
19.41 0.00 12500
19.42 0.00 12500
19.43 0.00 12500
19.44 0.00 12600
19.45 0.00 12600
19.46 0.00 12600
19.47 0.00 12600
19.48 0.00 12600
19.49 0.00 12600
19.50 0.00 12600
19.51 0.00 12600
19.52 0.00 12700
19.53 0.00 12700
19.54 0.00 12700
19.55 0.00 12700
19.56 0.00 12700
19.57 0.00 12700
19.58 0.00 12700
19.59 0.00 12800
19.60 0.00 12800
19.61 0.00 12800
19.62 0.00 12800
19.63 0.00 12800
19.64 0.00 12800
19.65 0.00 12800
19.66 0.00 12800
19.67 0.00 12900
19.68 0.00 12900
19.69 0.00 12900
19.70 0.00 12900
19.71 0.00 12900
19.72 0.00 12900
19.73 0.00 12900
19.74 0.00 13000
19.75 0.00 13000
19.76 0.00 13000
19.77 0.00 13000
19.78 0.00 13000
19.79 0.00 13000
19.80 0.00 13000
19.81 0.00 13000
19.82 0.00 13100
19.83 0.00 13100
19.84 0.00 13100
19.85 0.00 13100
19.86 0.00 13100
19.87 0.00 13100
19.88 0.00 13100
19.89 0.00 13200
19.90 0.00 13200
19.91 0.00 13200
19.92 0.00 13200
19.93 0.00 13200
19.94 0.00 13200
19.95 0.00 13200
19.96 0.00 13300
19.97 0.00 13300
19.98 0.00 13300
19.99 0.00 13300
20.00 0.00 13300
20.01 0.00 13300
20.02 0.00 13300
20.03 0.00 13300
20.04 0.00 13400
20.05 0.00 13400
20.06 0.00 13400
20.07 0.00 13400
20.08 0.00 13400
20.09 0.00 13400
20.10 0.00 13400
20.11 0.00 13500
20.12 0.00 13500
20.13 0.00 13500
20.14 0.00 13500
20.15 0.00 13500
20.16 0.00 13500
20.17 0.00 13500
20.18 0.00 13600
20.19 0.00 13600
20.20 0.00 13600
20.21 0.00 13600
20.22 0.00 13600
20.23 0.00 13600
20.24 0.00 13600
20.25 0.00 13700
20.26 0.00 13700
20.27 0.00 13700
20.28 0.00 13700
20.29 0.00 13700
20.30 0.00 13700
20.31 0.00 13700
20.32 0.00 13700
20.33 0.00 13800
20.34 0.00 13800
20.35 0.00 13800
20.36 0.00 13800
20.37 0.00 13800
20.38 0.00 13800
20.39 0.00 13800
20.40 0.00 13900
20.41 0.00 13900
20.42 0.00 13900
20.43 0.00 13900
20.44 0.00 13900
20.45 0.00 13900
20.46 0.00 13900
20.47 0.00 14000
20.48 0.00 14000
20.49 0.00 14000
20.50 0.00 14000
20.51 0.00 14000
20.52 0.00 14000
20.53 0.00 14000
20.54 0.00 14100
20.55 0.00 14100
20.56 0.00 14100
20.57 0.00 14100
20.58 0.00 14100
20.59 0.00 14100
20.60 0.00 14100
20.61 0.00 14200
20.62 0.00 14200
20.63 0.00 14200
20.64 0.00 14200
20.65 0.00 14200
20.66 0.00 14200
20.67 0.00 14200
20.68 0.00 14300
20.69 0.00 14300
20.70 0.00 14300
20.71 0.00 14300
20.72 0.00 14300
20.73 0.00 14300
20.74 0.00 14300
20.75 0.00 14400
20.76 0.00 14400
20.77 0.00 14400
20.78 0.00 14400
20.79 0.00 14400
20.80 0.00 14400
20.81 0.00 14400
20.82 0.00 14500
20.83 0.00 14500
20.84 0.00 14500
20.85 0.00 14500
20.86 0.00 14500
20.87 0.00 14500
20.88 0.00 14500
20.89 0.00 14600
20.90 0.00 14600
20.91 0.00 14600
20.92 0.00 14600
20.93 0.00 14600
20.94 0.00 14600
20.95 0.00 14600
20.96 0.00 14700
20.97 0.00 14700
20.98 0.00 14700
20.99 0.00 14700
21.00 0.00 14700
21.01 0.00 14700
21.02 0.00 14700
21.03 0.00 14800
21.04 0.00 14800
21.05 0.00 14800
21.06 0.00 14800
21.07 0.00 14800
21.08 0.00 14800
21.09 0.00 14800
21.10 0.00 14900
21.11 0.00 14900
21.12 0.00 14900
21.13 0.00 14900
21.14 0.00 14900
21.15 0.00 14900
21.16 0.00 14900
21.17 0.00 15000
21.18 0.00 15000
21.19 0.00 15000
21.20 0.00 15000
21.21 0.00 15000
21.22 0.00 15000
21.23 0.00 15000
21.24 0.00 15100
21.25 0.00 15100
21.26 0.00 15100
21.27 0.00 15100
21.28 0.00 15100
21.29 0.00 15100
21.30 0.00 15100
21.31 0.00 15200
21.32 0.00 15200
21.33 0.00 15200
21.34 0.00 15200
21.35 0.00 15200
21.36 0.00 15200
21.37 0.00 15200
21.38 0.00 15300
21.39 0.00 15300
21.40 0.00 15300
21.41 0.00 15300
21.42 0.00 15300
21.43 0.00 15300
21.44 0.00 15300
21.45 0.00 15400
21.46 0.00 15400
21.47 0.00 15400
21.48 0.00 15400
21.49 0.00 15400
21.50 0.00 15400
21.51 0.00 15400
21.52 0.00 15500
21.53 0.00 15500
21.54 0.00 15500
21.55 0.00 15500
21.56 0.00 15500
21.57 0.00 15500
21.58 0.00 15600
21.59 0.00 15600
21.60 0.00 15600
21.61 0.00 15600
21.62 0.00 15600
21.63 0.00 15600
21.64 0.00 15600
21.65 0.00 15700
21.66 0.00 15700
21.67 0.00 15700
21.68 0.00 15700
21.69 0.00 15700
21.70 0.00 15700
21.71 0.00 15700
21.72 0.00 15800
21.73 0.00 15800
21.74 0.00 15800
21.75 0.00 15800
21.76 0.00 15800
21.77 0.00 15800
21.78 0.00 15900
21.79 0.00 15900
21.80 0.00 15900
21.81 0.00 15900
21.82 0.00 15900
21.83 0.00 15900
21.84 0.00 15900
21.85 0.00 16000
21.86 0.00 16000
21.87 0.00 16000
21.88 0.00 16000
21.89 0.00 16000
21.90 0.00 16000
21.91 0.00 16000
21.92 0.00 16100
21.93 0.00 16100
21.94 0.00 16100
21.95 0.00 16100
21.96 0.00 16100
21.97 0.00 16100
21.98 0.00 16100
21.99 0.00 16200
22.00 0.00 16200
22.01 0.00 16200
22.02 0.00 16200
22.03 0.00 16200
22.04 0.00 16200
22.05 0.00 16300
22.06 0.00 16300
22.07 0.00 16300
22.08 0.00 16300
22.09 0.00 16300
22.10 0.00 16300
22.11 0.00 16300
22.12 0.00 16400
22.13 0.00 16400
22.14 0.00 16400
22.15 0.00 16400
22.16 0.00 16400
22.17 0.00 16400
22.18 0.00 16500
22.19 0.00 16500
22.20 0.00 16500
22.21 0.00 16500
22.22 0.00 16500
22.23 0.00 16500
22.24 0.00 16500
22.25 0.00 16600
22.26 0.00 16600
22.27 0.00 16600
22.28 0.00 16600
22.29 0.00 16600
22.30 0.00 16600
22.31 0.00 16700
22.32 0.00 16700
22.33 0.00 16700
22.34 0.00 16700
22.35 0.00 16700
22.36 0.00 16700
22.37 0.00 16700
22.38 0.00 16800
22.39 0.00 16800
22.40 0.00 16800
22.41 0.00 16800
22.42 0.00 16800
22.43 0.00 16800
22.44 0.00 16900
22.45 0.00 16900
22.46 0.00 16900
22.47 0.00 16900
22.48 0.00 16900
22.49 0.00 16900
22.50 0.00 16900
22.51 0.00 17000
22.52 0.00 17000
22.53 0.00 17000
22.54 0.00 17000
22.55 0.00 17000
22.56 0.00 17000
22.57 0.00 17100
22.58 0.00 17100
22.59 0.00 17100
22.60 0.00 17100
22.61 0.00 17100
22.62 0.00 17100
22.63 0.00 17100
22.64 0.00 17200
22.65 0.00 17200
22.66 0.00 17200
22.67 0.00 17200
22.68 0.00 17200
22.69 0.00 17200
22.70 0.00 17300
22.71 0.00 17300
22.72 0.00 17300
22.73 0.00 17300
22.74 0.00 17300
22.75 0.00 17300
22.76 0.00 17300
22.77 0.00 17400
22.78 0.00 17400
22.79 0.00 17400
22.80 0.00 17400
22.81 0.00 17400
22.82 0.00 17400
22.83 0.00 17500
22.84 0.00 17500
22.85 0.00 17500
22.86 0.00 17500
22.87 0.00 17500
22.88 0.00 17500
22.89 0.00 17500
22.90 0.00 17600
22.91 0.00 17600
22.92 0.00 17600
22.93 0.00 17600
22.94 0.00 17600
22.95 0.00 17600
22.96 0.00 17700
22.97 0.00 17700
22.98 0.00 17700
22.99 0.00 17700
23.00 0.00 17700
23.01 0.00 17700
23.02 0.00 17800
23.03 0.00 17800
23.04 0.00 17800
23.05 0.00 17800
23.06 0.00 17800
23.07 0.00 17800
23.08 0.00 17800
23.09 0.00 17900
23.10 0.00 17900
23.11 0.00 17900
23.12 0.00 17900
23.13 0.00 17900
23.14 0.00 17900
23.15 0.00 18000
23.16 0.00 18000
23.17 0.00 18000
23.18 0.00 18000
23.19 0.00 18000
23.20 0.00 18000
23.21 0.00 18100
23.22 0.00 18100
23.23 0.00 18100
23.24 0.00 18100
23.25 0.00 18100
23.26 0.00 18100
23.27 0.00 18200
23.28 0.00 18200
23.29 0.00 18200
23.30 0.00 18200 *

## Structures
River Structures Inventory Worksheet |  | Structures Geometry and Location Worksheet
Structure Types |  | Critical Elevations |  | Datum | Source of Data | Location |  |  | Included?
Bridges |  | Bridge: Low Steel |  | NAVD88 | As-Built Drawings | Left Bank |  |  | Yes
Levee |  | Bridge: Road Decking |  | NGVD29 | Site Survey | Right Bank |  |  | No
Floodwall |  | Levee: Crest Elevation |  | MSL | Lidar | Channel
Emergency Closures |  | Levee: Toe Elevation |  | COE1912 | City\County Platt or Contour Map
Temporary Flood Protection |  | Floodwall: Crest Elevation |  | Local | USGS Topo Map
Dam |  | Dam: Crest elevation |  | Other (specify) | GPS Survey
Dredging |  | Reservoirs: Crest Elevation |  |  | Estimated
Wing Dikes or Channel Control |  | Temp Flood Protection: Crest |  |  | Unknown
Building |  | Temp Flood Protection: Base
General Obstacles to Flow
Floodplain Development
Other
Structure Type | Structure Name | Critical Elevation | Critical Elevation | Elevation Datum | Source of Structure Elevation Data | Location | Location | Location | Included in |  | Bridge Diagrams from HEC-RAS
|  | Description | (ft) |  |  | (LB, RB or Channel) | (River mi from gage) | (U\S or D\S from gage) | Hydraulic Model?
| GAGE | [9 empty] | Ferguson Rd
Bridges | Ferguson Rd. | Bridge: Road Decking | 777 | NAVD88 | Unknown | Channel |  | D\S | Yes |  | Insert Structures Diagrams from HEC-RAS after model has been constructed
Bridges | Ferguson Rd. | Bridge: Low Steel | 772.3 | NAVD88 | Unknown | Channel |  | D\S | Yes
Bridges | Lower Huntington Rd | Bridge: Road Decking | 773 | NAVD88 | Unknown | Channel |  | D\S | Yes |  |  | Diagram for each bridge should show:
Bridges | Lower Huntington Rd | Bridge: Low Steel | 770 | NAVD88 | Unknown | Channel |  | D\S | Yes |  |  | (1) WS elevations at and below the low chord
Bridges | Airport Expressway | Bridge: Road Decking | 773 | NAVD88 | Unknown | Channel |  | D\S | Yes |  |  | (2) Bridge Geometry
Bridges | Airport Expressway | Bridge: Low Steel | 769 | NAVD88 | Unknown | Channel |  | D\S | Yes |  |  | (3) Ineffective flow areas
Levee | Right Levee | Levee: Crest Elevation | 765.8 | NAVD88 | Unknown | Right Bank |  | D\S | Yes
Levee | Right Levee | Levee: Toe Elevation |  | NAVD88 | Unknown | Right Bank |  | D\S | Yes
Levee | Left Levee | Levee: Crest Elevation |  | NAVD88 | Unknown | Left Bank |  | D\S | Yes
Levee | Left Levee | Levee: Toe Elevation |  | NAVD88 | Unknown | Left Bank |  | D\S | Yes
Bridges | Bluffton Road | Bridge: Road Decking | 767.3 | NAVD88 | Unknown | Channel |  | D\S | Yes
Bridges | Bluffton Road | Bridge: Low Steel | 763.2 | NAVD88 | Unknown | Channel |  | D\S | Yes | LS@22 ft
Levee | Right Levee | Levee: Crest Elevation |  | NAVD88 | Unknown | Right Bank |  | D\S | Yes
Levee | Right Levee | Levee: Toe Elevation |  | NAVD88 | Unknown | Right Bank |  | D\S | Yes
Bridges | Norfolk Southern Railway | Bridge: Road Decking | 775.8 | NAVD88 | Unknown | Channel |  | D\S | Yes
Bridges | Norfolk Southern Railway | Bridge: Low Steel | 762.8 | NAVD88 | Unknown | Channel |  | D\S | Yes | LS@22 ft
Bridges | Hale Ave\St. Joseph | Bridge: Road Decking | 762 | NAVD88 | Unknown | Channel |  | D\S | Yes
Bridges | Hale Ave\St. Joseph | Bridge: Low Steel | 759.5 | NAVD88 | Unknown | Channel |  | D\S | Yes | LS@20 ft
Bridges | Taylor Street | Bridge: Road Decking | 763.4 | NAVD88 | Unknown | Channel |  | D\S | Yes
Bridges | Taylor Street | Bridge: Low Steel | 760 | NAVD88 | Unknown | Channel |  | D\S | Yes | LS@21ft
Bridges | CSX | Bridge: Road Decking | 766.28 | NAVD88 | Unknown | Channel |  | D\S | Yes
Bridges | CSX | Bridge: Low Steel | 763.48 | NAVD88 | Unknown | Channel |  | D\S | Yes
Bridges | Jefferson Blvd West | Bridge: Road Decking | 763.78 | NAVD88 | Unknown | Channel |  | D\S | Yes
Bridges | Jefferson Blvd West | Bridge: Low Steel | 761.5 | NAVD88 | Unknown | Channel |  | D\S | Yes | LS@22 ft
Levee | Left Levee | Levee: Crest Elevation |  | NAVD88 | Unknown | Left Bank |  | D\S | Yes
Levee | Left Levee | Levee: Toe Elevation |  | NAVD88 | Unknown | Left Bank |  | D\S | Yes
Bridges | Foot Bridge | Bridge: Road Decking |  | NAVD88 | Unknown | Channel |  | D\S | No |  | Lower Huntington Rd.
Bridges | Foot Bridge | Bridge: Low Steel |  | NAVD88 | Unknown | Channel |  | D\S | No
Bridges | Main Street West | Bridge: Road Decking | 760.1 | NAVD88 | Unknown | Channel |  | D\S | Yes
Bridges | Main Street West | Bridge: Low Steel | 757.3 | NAVD88 | Unknown | Channel |  | D\S | Yes | LS@20 ft
Insert Structures Diagrams from HEC-RAS after model has been constructed
Diagram for each bridge should show:
(1) WS elevations at and below the low chord
(2) Bridge Geometry
(3) Ineffective flow areas
Airport Expressway\Pauling Rd.
Insert Structures Diagrams from HEC-RAS after model has been constructed
Diagram for each bridge should show:
(1) WS elevations at and below the low chord
(2) Bridge Geometry
(3) Ineffective flow areas
Insert Structures Diagrams from HEC-RAS after model has been constructed
Bluffton Rd.
Insert Structures Diagrams from HEC-RAS after model has been constructed
Diagram for each bridge should show:
(1) WS elevations at and below the low chord
(2) Bridge Geometry
(3) Ineffective flow areas
Norfolk Southern Railway
Hale Ave\St. Joseph
Taylor Street
CSX
Jefferson
Main Street West

## Tech Doc
Technical Documentation Requirements
1.0 Introduction
1.1 Overview
Purpose of the study and summary of modeling and GIS approach
1.2 Location
Location and extent of the study area
|  |  | Figure 1. | USGS Gage Location (NOTE: same as [Location Map] "USGS Gage Location Map")
Regional View of USGS Gage Location, showing City, County and Roads.
Layers: USGS gage location
Basemap: Standard Google "Map" View: roads, corporate boundaries, county boundaries, state boundaries
|  |  | Figure 2. | Project Overview Map of the study area (NOTE: same as [Location Map] "Overview Map")
Project View zoomed to the extent boundaries.
Layers: Upstream/Downstream study extent boundaries, stream gage(s),
Basemap: aerial photo, roads, corporate boundaries, county boundaries
1.3 Flood History
Description of the flood history and importance of flood mapping for the community and/or general area.
2.0 Model Analysis
2.1 Hydrology
2.1.1 Stream Gage
A description of the stream gage, its drainage area, and its period of record.
2.1.2 Study Area Extent Analysis
A description of hydrologic techniques used to determine local flow contribution to the study area extent (if applicable)
2.2 Hydraulics
2.2.1 Hydraulic Model
A description of the model and version used. Describe rationale for choosing a one- or two dimensional analysis and a steady or unsteady flow rate.
Describe assumptions made during the modeling analysis
|  |  |  | Figure 3. | Downstream boundary conditions rating curve (if applicable)
2.2.2 Calibration
A description of the calibration and verification techniques used.
2.2.3 Results
An error analysis on the flood depths based on high-water mark observations and available gage data.
|  |  |  | Table 2. | Comparison of hydraulic-model output and surveyed high water mark elevations from a calibration event.
|  |  |  | Figure 4. | USGS station rating curve vs. the model derived rating curve. Plot will show the difference between the rating curves on a secondary axis.
Rating curve should show that model was calibrated to an acceptable tolerance to within of 0.1 ft to 0.5 ft of the measured rating curve.
|  |  |  | Figure 5. | Profile view of the hydraulic model water surface showing that water surface(s) was\were calibrated to the HWM data.
|  |  |  | Figure 6. | Flood inundation map depicting the calibration and location of HWM data
Layers: upstream/downstream study area boundaries, stream gage, HWM points, lines or polygons, inundation aerial
Basemap: aerial photo
3.0 Map Development
3.1 Topographic Data
A description of the topographic data source, vertical\horizontal accuracy, capture date and format
3.2 Processing Techniques
A discussion of the GIS techniques used to convert the hydraulic model profiles into depth grids and inundation polygons
4.0 Conclusions
4.1 Summary
A summary of the results of the study
4.2 Lessons Learned
Any lessons learned with a description of potential solutions and\or difficulties associated with the potential solutions

## Metadata
Metadata Requirements
Applies to:
All geospatial data submitted to NWS. See "X" values below for specific product requirements.
Method for Data Entry:
(1) Default metadata should be used from the source data, whenever possible. If source data is not available OR does not contain all field below
then the source data should be supplemented with the text & metadata fields below.
(2) Use ArcGIS ArcCatalog for data entry, so that metadata file is "attached" to shapefile and grids and can be viewed with ArcGIS catalog
(3) Populate the following information in the FGDC metadata. Lowercase text may be copied directly.
UPPERCASE text should be substituted with product specific info.
ESRI ArcCatalog Fields | Metadata XML Tags | STUDY AREA | MODEL CROSS-SECTIONS | GAGE LOCATION POINT | FEMA DFIRM FLOODWAY | FEMA DFIRM 1% | FEMA DFIRM 0.2% | FLOOD CONTROL STRUCTURES | LEVEE RISK AREA | DEPTH GRIDS | POLYGONS |  | Metadata Text to Enter
Tags | <metadata><idinfo><keywords><theme><themekey> | X | X | X |  |  |  | X |  | X | X | STATE MAP WAS PRODUCTED IN, NAME OF COMMUNITY, flood, flood inundation mapping, hydrologic prediction, hydraulic, modeling,
Summary | <metadata><idinfo><descript><purpose> | X | X | X |  |  |  | X |  | X | X | This data set was developed exclusively for use with the National Weather Service's (NWS) Advanced Hydrologic Prediction Service (AHPS) website.
Description | <metadata><idinfo><descript><abstract> | X | X | X |  |  |  | X |  | X | X | DESCRIBE THE DATA SET. The Flood Inundation Map Graphics show the lateral extent of projected flooding on local map backgrounds.
Credits | <metadata><idinfo><ptcontac><datacred> | X | X | X |  |  |  | X |  | X | X | XXXX agency conducted the hydraulic analysis and GIS analysis to produce the inundation data. NWS provided the QA\QC review of the data. Funding was received from XXXX for this project.
Use limitations | <metadata><idinfo><useconst> | X | X | X |  |  |  | X |  | X | X | Users must assume responsibility to determine the appropriate use of this data. Users should be aware of the limitations of this dataset if using for critical application. Flood Inundation Maps will show the extent of flooding expected spatially over a given area. This will indicate when roadways, streets, buildings, airports, etc. are likely to be impacted by floodwaters. The accuracy of the mapping depends on the degree of accuracy of DEM data available for use in the GIS application, plus other factors.
Purpose | <metadata><idinfo><descript><purpose> | X | X | X |  |  |  | X |  | X | X | This data set was developed for use with the National Weather Service's (NWS) Advanced Hydrologic Prediction Service (AHPS) website
Supplemental Information | <metadata><idinfo><descript><supplinf> | X | X | X |  |  |  | X |  | X | X | The initial target audience is the state and local agencies that must make emergency operational decisions during flooding events. However, since the graphics are easy to view, anyone with an interest during these events can make use of the maps, including the Federal Emergency Management Agency (FEMA), the U.S. Geological Survey (USGS), Corps of Engineers (COE), state and local emergency managers, the media, and the general public.
Date of Publication | <metadata><idinfo><timeperd><timeinfo><sngdate><caldate> | X | X | X |  |  |  | X |  | X | X | DATE AND YEAR
Contact Info | <metadata><idinfo><metainfo><metc><cntinfo> | X | X | X |  |  |  | X |  | X | X | Comments regarding the Flood Inundation Maps can be made here (http://www.weather.gov/survey/nws-survey.php?code=inundate). CONTACT INFO FOR AGENCY THAT PRODUCED THE DEPTH GRID AND POLYGONS.
Horizontal Datum | <metadata><spref><horizsys> | X | X | X |  |  |  | X |  | X | X | World Geodetic System of 1984 Web Mercator (Auxillary Sphere)
Vertical Datum | <metadata><spref><vertdef> | [8 empty] | X | X | North American Vertical Datum of 1988
Horizontal Accuracy | <metadata><dataqual><posacc><horizpa><horizpar> | [6 empty] | X |  | X | X | As with any engineering analysis of this type, variation from the estimated flood heights and floodplain boundaries is possible. Details of the process used to produce this data can be found in project documentation available from the data contact person. Horizontal accuracy was tested by evaluating boundaries to best available topographic dataset.
Vertical Accuracy | <metadata><dataqual><posacc><vertacc><vertaccr> | [8 empty] | X | X | As with any engineering analysis of this type, variation from the estimated flood heights and floodplain boundaries is possible. Details of the process used to produce this data can be found in project documentation available from the data contact person. Vertical accuracy was tested by evaluating boundaries to best available topographic dataset
|  | X | Complete
Comments: |  | X | Partially complete. Needs Modification or addition of "boilerplate" NWS metadata text
Date of publication contains Years and not the month/day |  | X | Missing. Missing Metadata tags
For depth and polygon files...did not see complete METADATA through Arccatalog or via the xml files

## File Structure
File Structure Requirements
| Deliverables by Phase |  |  |  | AHPS Deliverables - Standard Directory Format |  |  | Name {file name}
| Phase 1 | Phase 2A | Phase 2B | Phase 3
[5 empty] | NWSLID.MM.DD.YYYY. Zip | (ex: IOWI4.01.22.12.zip)
\hydraulics\
|  | R |  |  |  |  | Hydraulic Model Files
\GIS\
\depth_ grids\
|  |  | R |  |  |  |  | Depth Grids {elev_feet_tenth}
\polygons\
|  |  | R |  |  |  |  | Polygons {elev_feet_tenth.shp}
\base_data\
| O |  | R |  |  |  |  | Study Area {study_area.shp}
| O |  | R |  |  |  |  | Gage Location Point {gage.shp}
| O |  | O |  |  |  |  | FEMA Floodway {FEMA_fldwy.shp}
| O |  | O |  |  |  |  | FEMA DFIRM 1% {FEMA_1pct.shp}
| O |  | O |  |  |  |  | FEMA DFIRM 0.2% {FEMA_02pct.shp}
| O |  | O |  |  |  |  | Flood Control Structures {flood_cntrl.shp}
| O |  | O |  |  |  |  | Levee Risk Area {levee_ risk_area.shp}
\supplemental\
|  | R | [5 empty] | Preliminary Floodplain Boundary {pre_elev_feet_tenth.shp}
| O | [6 empty] | Terrain Footprint {terrain.shp}
| O | O | R |  |  |  |  | Model Cross-Sections {xs.shp}
|  | R | [5 empty] | High Water Marks {HWM.shp}
\documentation\
|  |  |  | R |  |  | Project Development Template {FIM.NWSLID.DATE.xls}
| R | R | R |  |  |  | Technical Summary Document {FIM.NWSLID.DATE.doc}
|  | O |  |  |  |  | Rating Curve Extension Text File {rating.NWSLID.DATE.txt}
| O | O | O | O |  |  | Any Supplemental Documentation Developed During the Project
Additional Deliverables - Outsize of Zip File
|  |  | O |  |  | Terrain Data (point cloud, DEM, TIN or contours)
O = Optional
R = Required

## Terrain
Terrain Metadata
Raw Terrain Data
| Source: | Indiana?
| Publication Date: | 2011?
| Acquisition Date: | 2012?
| Vertical Accuracy (ft or m): | 0.12 ft
| Nominal Point (or Post) Spacing (ft or m): | 3-m (3.3 ft)
| Horizontal Projection: | ?
| Vertical Datum: | ?
Post-Processed Terrain Data
| Format (DEM or TIN): | DEM
| DEM Cell Size (ft or m): | 3m
Horizontal Projection:
| Vertical Datum: | NAVD88

## Spatial Calc
Spatial Calculations
VERTCON Calculation Results |  |  | Comments on Vertical Datum Quality
http://www.ngs.noaa.gov/cgi-bin/VERTCON/vert_con.prl
| Latitude: | 40 59 16
| Longitude: | 85 06 43
| NGVD 29 height: | 748.97 feet
| Datum shift(NAVD 88 minus NGVD 29): | -0.512 feet
| Converted to NAVD 88 height: | 748.458 feet
Google Maps Display Scale
http://blogs.esri.com/Support/blogs/mappingcenter/archive/2009/03/19/How-can-you-tell-what-map-scales-are-shown-for-online-maps_3F00_.aspx

## Local Flow Analysis
Local Flow Analysis - Static FIM Reaches Greater than 5 miles
Guideline |  | Table 1. Site Parameters and TP-40 Information
[6 empty] | TP-40 | Table 2 | Above
|  |  | Distance | Local | % of Total | 100-year, | 2 x Min | or below
|  |  | from gage | Area | Contributing | 24-hour | Q delta | 2x Min
|  |  | (mi) | (mi2) | Area (%) | Qp (cfs) | (cfs) | Q delta?
Max U/S Reach
Justification: |  | Min U/S Reach
Min D/S Reach
Max D/S Reach
[6 empty] | ^ | ^
[6 empty] | ^ | ^
[6 empty] | ^ | ^
[6 empty] | ^ | ^
| Table 2. 24-hour duration UHGS |  |  |  |  | ===== | ===== | Table 3. USGS Rating Curve at the Gage
| Time | Max U/S | Min U/S | Max D/S | Min D/S |  |  | Stages | Q | Qdelta = | Minimum
| (hrs) | (cfs) | (cfs) | (cfs) | (cfs) |  |  | Above FS (ft) | (cfs) | Qhigh-Qlow | Qdelta
Procedure:
100-yr, 24-hour rainfall amounts for the US from TP-40
The peak flow from a 100-year, 24-hour duration storm, when applied to a synthetic UHG and assuming a high runoff efficiency (90%), should cause an increase in stage less than 2 times the stage interval. This guideline applies to all stages above flood stage.
The local flow should not cause a significant deviation between the stage observed at the gage and the stages observed at the most upstream and downstream points. The only way to evaluate this condition is to through scenario evaluation of the local basin’s hydrologic response.
Because the rating curve will likely not be available for the most upstream and downstream points, it must be assumed that the gage rating approximates the upstream/downstream ratings. Only stages above flood stage are evaluated to determine if they stage/flow relationships meet the criteria. Due to the shape of the rating curve, stages below flood stage will have a significantly steeper slope and will likely produce an overly conservative number, if used to evaluate the stage/flow relationship. The focus should be on significant flows and impacts above flood stage, and the selection of flood stage or flow above flood stage allow the worst case scenario of an extreme local flows, on top of existing high flow conditions, to be evaluated.
A significant deviation is defined as 2 times the stage interval. Twice the stage interval was selected as a rule of thumb for the acceptable tolerance for error that would be generated from a significant storm. Assuming the observed flows are 100% accurate at the gage, and that the largest mapping interval that would be implemented in a map library is 1.0 ft, the stages at the upstream and downstream locations should approximately within -+ 2.0 ft of the observed for a significant rainfall event. The 100-yr, 24 hour design storm was selected as the evaluation criteria, as it is the most extreme event published in the NOAA TP-40, but is, in most cases, less than the most extreme event observed. Selecting a standard design storm from the the NOAA TP-40 will allow for the standard to be repeated at all locations. The 90% runoff efficiency assumes a relatively high degree of saturation, but not complete saturation. This runoff efficiency is consistent with an AMC Type 3 (wet) condition for an moderately permeable soil with fair cover.
The Unit Hydrograph used to develop the Qp estimate should be what the RFC typically uses for local segments in the adjoining areas. The UHG duration should be adjusted to 24-hours.
1. Identify sub-basin outlet “break points” for at least 2 locations upstream and 2 locations downstream.
2. The RFC will use IHABBs to create sub-basin boundaries and develop UHGs with an appropriate UHG method. The selected UHG method should be consistent with UHG methods applied in neighboring basins. The duration of the UHG should be transformed to a 24-hour duration.
3. Identify the rainfall produced by the 100-yr, 24 hour duration design storm in NOAA TP-40.
Calculate Qp for each UHG based on the 100-year, 24-hour duration design storm assuming a high runoff efficiency of 90%.
4. Calculate the flow threshold that cannot be exceeded by Qp from the rating curve.
  a. Collect\determine:
    i. the rating curve at the gage.
    ii. flood stage
    iii. Determine the mapping interval (i) for the flood inundation mapping library.
  b. Calculate the difference in flow at a regular mapping interval for all stages above flood stage. Q delta = Q stage 1 - Q stage 2
  c. Determine the minimum differential in flow (Q delta) for the entire rating curve. Twice minimum differential in flow (2 * (Q delta)) is the constraining value flow threshold the cannot exceeded by Qp.
7. Compare Qp to (2 * (Q delta)) for all UHGs to determine suitability

## Version
Version Changes
0.1 | Baseline
0.11 | Added Flood Imapcts to [Flood History]
Added flood impacts information to the Task List: Site Suitability Evaluation
Fixed font alignment issues on header of Task List
0.12 | Added HWM Shapefile to Phase 2A Deliverable
Changed "HWM Profile Validation" to "Water Surface Elevation Validation"